MASTER EXECUTION BLUEPRINT

Working Name: TAJRIBTI (تجربتي)

Egypt's Consumer Intelligence Platform — from Approved Sprint to Operating Company

| Field | Detail |
| --- | --- |
| Source of Truth | Investment Committee Memo — Final Edition v1.0 (26 July 2026) |
| Actual IC Decision | CONDITIONAL APPROVAL — $15–25K / 60-day validation sprint only |
| Status of this document | Execution plan for the approved sprint (Track 0), plus a contingent full-company blueprint (Track 1) ready to activate on a GO decision |
| Country | Arab Republic of Egypt |
| Date | 26 July 2026 |
| Version | 1.0 |

HOW TO READ THIS DOCUMENT • Track 0 (Sections 1–3 intro, and flagged throughout): what is funded and staffed TODAY under the approved sprint. This is the only track with real budget authority right now. • Track 1 (the bulk of this document): the full operating company — mission, departments, org chart, processes, product, tech, KPIs. Built in full detail so execution can start on Day 1 of a GO decision with zero re-planning delay. • Every department, hire, and dollar figure in Track 1 is CONTINGENT on the sprint's Go/No-Go gate (IC Memo §11). Nothing here authorizes spending beyond the approved $15–25K until that gate is passed.

# Table of Contents

# Track 0 — What Is Actually Funded Right Now

Per IC Memo v1.0 §11, the only authorized activity today is a 60-day, $15,000–25,000 commercial validation sprint. Everything below is that sprint, staffed and scheduled.

| Role | Who | Time Commitment | Sprint Deliverable |
| --- | --- | --- | --- |
| Founder/CEO | 1 person (full-time) | 100% | Owns brand interviews, LOIs, go/no-go report to IC |
| Commercial lead (contract or co-founder) | 1 person | 60–80% | Runs the 30–50 brand interviews, drafts LOIs |
| Analyst (part-time/contract) | 1 person | 30–40% | Builds the bottom-up Egypt TAM model, competitor deep-dive on Marketeers Research |
| Legal advisor (retainer, hours-based) | External | As needed | Reviews LOI language and PDPL exposure before any consumer data is touched |

### Sprint budget breakdown (fits inside the $15–25K envelope)

| Item | Estimate (USD) |
| --- | --- |
| Founder/commercial lead time (opportunity cost, not cash) | $0 cash / in-kind |
| Contract analyst (60 days, part-time) | $3,000–5,000 |
| Legal review (LOI templates, PDPL exposure check) | $2,000–4,000 |
| Landing page + lead capture tooling | $500–1,500 |
| Travel/meetings (Cairo, Giza, Alexandria brand visits) | $1,500–3,000 |
| Contingency | $3,000–5,000 |
| TOTAL | $15,000–25,000 — matches IC-approved envelope |

No engineering hire, no office lease, no app build happens in Track 0. Everything past this point is Track 1 — planned in full, funded only on GO.

# Phase 1 — Company Design (Track 1, contingent)

### Mission

Replace guesswork in product launches with real-time, consented consumer truth — starting with Egypt's FMCG, beauty, and pharma-OTC sectors.

### Vision

To become the default consumer-intelligence layer behind every new product launch in Egypt within 3 years, and across the wider MENA region within 5–7 — contingent on Egypt unit economics being proven first, per IC Memo scaling guidance.

### Core Values

- Evidence over opinion — every internal decision cites data or is labeled a bet.

- Consent is non-negotiable — no dark patterns in data collection, ever.

- Speed beats polish — ship the smallest thing that answers a real question.

- Data is the product, not the exhaust — the dashboard is what brands actually pay for.

- Egypt-first, not Egypt-adapted — Arabic, local payment rails, and local retail partners are the default, not a localization afterthought.

### Company DNA

Lean, B2B-sales-led, data-obsessed. Not a consumer-growth-hacking company that happens to sell data — a data company that happens to use free samples as its acquisition channel.

### Brand Positioning

"Egypt's Consumer Intelligence Platform." Never described internally or externally as a sampling company, coupon app, or research agency.

### Competitive Positioning

| Axis | Tajribti | Marketeers Research | Traditional research (BioNixus, Mena Intel, etc.) | BTL activation agencies |
| --- | --- | --- | --- | --- |
| Physical sampling network | Yes — core mechanic | No | No | Yes, but unmeasured |
| AI-generated insights | Yes | Yes | Limited | No |
| Data turnaround | Hours–days | Weeks | Weeks | No structured data |
| Egypt-first UX/payments | Yes (from Day 1) | Partial | Partial | N/A |

### Unique Selling Proposition

The only Egyptian platform that converts a free product trial into structured, brand-actionable consumer data within 24 hours — not weeks.

# Phase 2 — Department Design (Track 1)

### CEO Office

| Field | Detail |
| --- | --- |
| Mission | Set strategy, own investor/IC relationship, final call on brand-partnership terms |
| Key Responsibilities | Board/IC reporting cadence, capital allocation, hiring bar |
| KPIs | Runway, sprint-to-GO conversion, brand pipeline value |
| Required Team | Founder/CEO (Y1); EA (Y2) |
| Key Dependencies | OKR-setting, weekly all-hands, monthly IC/board update |

### Operations

| Field | Detail |
| --- | --- |
| Mission | Run field sampling logistics end-to-end without owning warehouses or a fleet |
| Key Responsibilities | Retail-partner relationships, campaign fulfillment, field staff scheduling, fraud monitoring |
| KPIs | Fulfillment SLA, cost-per-sample, fraud rate |
| Required Team | Ops Manager (Y1); 2 field coordinators (Y2) |
| Key Dependencies | Outsourced logistics partner is a hard dependency — no owned fleet in Y1 per IC risk mitigation |

### Technology (Engineering)

| Field | Detail |
| --- | --- |
| Mission | Ship and run the app, dashboards, and data pipeline reliably |
| Key Responsibilities | Mobile app, brand dashboard, backend, QR/fraud systems, uptime |
| KPIs | Uptime, deploy frequency, P1 incident count |
| Required Team | CTO + 2 engineers (Y1); +3 (Y2) |
| Key Dependencies | Depends on Product for scope, on AI/Data for the insights layer |

### Product

| Field | Detail |
| --- | --- |
| Mission | Decide what gets built and why, owned by customer evidence not opinion |
| Key Responsibilities | Roadmap, feature specs, user research, pricing-package design |
| KPIs | Feature adoption, campaign completion rate, NPS |
| Required Team | Product Manager (Y1, can be CEO initially); dedicated PM (Y2) |
| Key Dependencies | Depends on Sales/CS for brand feedback loop |

### Marketing

| Field | Detail |
| --- | --- |
| Mission | Acquire and retain the consumer side of the two-sided marketplace |
| Key Responsibilities | Consumer acquisition campaigns, community building, brand awareness for Tajribti itself |
| KPIs | Consumer CAC, app installs, activation rate |
| Required Team | Marketing Manager (Y2 — not funded in Y1 lean build) |
| Key Dependencies | Depends on Product for in-app rewards mechanics |

### Sales / Brand Partnerships

| Field | Detail |
| --- | --- |
| Mission | Sign and renew brand clients — the actual revenue engine |
| Key Responsibilities | Outbound to target 20 FMCG accounts, pricing negotiation, contract renewal |
| KPIs | Pipeline value, win rate, average contract value, renewal rate |
| Required Team | Head of Brand Partnerships (Y1, the sprint's commercial lead converts into this role on GO) |
| Key Dependencies | Depends on Ops for delivery proof-points, Data for the insights that close deals |

### Customer Success

| Field | Detail |
| --- | --- |
| Mission | Keep signed brands renewing by proving ROI campaign after campaign |
| Key Responsibilities | Onboarding new brand clients, campaign reporting, renewal conversations |
| KPIs | Renewal rate, NPS (brand side), time-to-first-insight |
| Required Team | CS lead (Y2) |
| Key Dependencies | Depends on Data/AI for report quality |

### Finance

| Field | Detail |
| --- | --- |
| Mission | Keep runway visible and spending inside approved envelopes |
| Key Responsibilities | Budgeting, invoicing brands, cash-flow tracking, IC/board financial reporting |
| KPIs | Burn rate, runway months, DSO (days sales outstanding) |
| Required Team | Fractional CFO / bookkeeper (Y1); full-time Finance Lead (Y2) |
| Key Dependencies | Reports actuals against every dollar figure in this blueprint monthly |

### Legal & Compliance

| Field | Detail |
| --- | --- |
| Mission | Keep the company inside Egyptian data-protection and consumer-protection law |
| Key Responsibilities | PDPL (Law 151/2020) compliance, brand contracts, consumer terms of use, IP protection |
| KPIs | Zero compliance incidents, contract turnaround time |
| Required Team | External counsel (Y1, retainer); in-house counsel (Y3) |
| Key Dependencies | Hard gate before any consumer data collection begins — see Phase 7 Security |

### HR / People

| Field | Detail |
| --- | --- |
| Mission | Hire correctly for a lean, execution-heavy team and keep them |
| Key Responsibilities | Recruiting, culture, compensation bands, performance reviews |
| KPIs | Time-to-hire, retention, engagement |
| Required Team | Founder-led (Y1); dedicated HR (Y2) |
| Key Dependencies | Depends on Finance for compensation budget |

### Support

| Field | Detail |
| --- | --- |
| Mission | Resolve consumer and brand issues fast enough to protect trust |
| Key Responsibilities | Consumer app support, brand dashboard support, fraud dispute handling |
| KPIs | Response time, resolution time, CSAT |
| Required Team | Shared with Ops/CS in Y1; dedicated team Y2 |
| Key Dependencies | Depends on Tech for tooling (ticketing, escalation) |

### AI / Data Science

| Field | Detail |
| --- | --- |
| Mission | Turn raw survey and sampling data into the insight narratives brands actually pay for |
| Key Responsibilities | Fraud-detection models, segmentation, purchase-intent prediction, insight-generation pipeline |
| KPIs | Model accuracy, insight turnaround time, fraud catch rate |
| Required Team | Data Lead (Y1, can be fractional); ML engineer (Y2) |
| Key Dependencies | Depends on Tech for data pipeline, on real campaign volume to train on |

# Phase 3 — Organizational Chart & Hiring Roadmap

### Year 1 (post-GO: Lean MVP team, ~10–12 people)

CEO → CTO, Head of Brand Partnerships (Sales), Ops Manager, Product Manager (or CEO doubling this role initially), Data Lead → 2 engineers, 2 field coordinators, fractional CFO, fractional legal counsel.

### Year 2 (proven-model team, ~25–35 people)

Add: Marketing Manager, Customer Success lead + 2 CS reps, dedicated Finance Lead, dedicated HR, dedicated Support team (2), ML engineer, +3 engineers, regional Ops leads for Alexandria/Giza/New Cairo/6th October.

### Year 3 (regional-option team, ~50–70 people — conditional on GCC gate in IC Memo §9)

Add: VP Sales, VP Product, in-house counsel, GCC country leads (Saudi Arabia, UAE first), dedicated Data Science team, Retail Media / Enterprise API team.

### Reporting Structure

CEO ← CTO, Head of Sales, Head of Ops, CFO, Head of Product, Head of Data/AI (Y1 direct reports). Marketing, CS, HR, Support, Legal join as direct reports from Year 2 as they are staffed.

### Decision Hierarchy

| Decision Type | Owner | Example |
| --- | --- | --- |
| Strategic (capital, new markets, pivots) | CEO + Investment Committee | GCC expansion timing |
| Tactical (department roadmap, hiring within budget) | Department Head | Which retail partner to prioritize this quarter |
| Operational (day-to-day execution) | Team Lead / IC | Which brand campaign ships this week |

# Phase 4 — Business Processes

| Process | Steps | Owner | SLA / Automation |
| --- | --- | --- | --- |
| Lead (brand) | Inbound/outbound → qualification → discovery call → proposal | Sales | Automated lead scoring from Year 2 |
| Sales | Proposal → pricing negotiation → contract → campaign kickoff | Sales + Legal | Contract turnaround target: 5 business days |
| Customer onboarding (brand) | Kickoff call → campaign design → target segment definition → go-live | Customer Success | Time-to-first-campaign target: 10 business days |
| Payments | Brand invoiced per campaign or subscription tier → payment via bank transfer/corporate card | Finance | Automated invoicing from Year 2; DSO target <30 days |
| Support (consumer) | In-app ticket → triage → resolution | Support | Response <4 hrs, resolution <24 hrs |
| Operations (fulfillment) | Campaign brief → retail-partner site selection → sample logistics → field execution → QR validation | Operations | Outsourced logistics partner; fulfillment SLA 48–72 hrs from campaign go-live |
| Marketing (consumer acquisition) | Channel plan → content/campaign → install → activation | Marketing | Consumer CAC target <$2 (IC Memo target, unvalidated) |
| Retention (consumer) | Rewards, gamification, referral prompts, weekly re-engagement triggers | Product + Marketing | Target: recurring reason to open app weekly |
| Renewal (brand) | Campaign report delivery → ROI review call → renewal proposal | Customer Success + Sales | Renewal conversation starts 30 days pre-expiry |
| Escalation | Fraud flag / data breach / brand complaint → immediate Ops+Legal+CEO loop | Ops + Legal + CEO | P1 incidents: CEO notified within 1 hour |
| Automation backbone | Campaign creation, consumer segmentation, reward distribution, survey generation, AI reporting, invoicing, QR validation, notifications | Technology + AI/Data | Everything repetitive is automated by design — see Phase 7 |

# Phase 5 — Complete Customer Journey

### Journey A — Brand Client (B2B, the paying customer)

| Stage | Experience |
| --- | --- |
| Discovery | Outbound from Sales, or inbound via case-study content / referral |
| Research | Discovery call, sample dashboard walkthrough, ROI case study |
| Purchase | Contract signed, campaign package selected (Starter/Growth/Enterprise) |
| Onboarding | Campaign design workshop, target segment defined, retail sites selected |
| Usage | Campaign runs; brand watches live dashboard fill with tagged consumer responses |
| Support | Dedicated CS contact for campaign-in-flight questions |
| Renewal | ROI report delivered within days of campaign close; renewal conversation follows |
| Referral | Case study shared with brand's peer network; referral incentive on next contract |
| Expansion | Brand adds AI dashboard subscription, consumer panel access, or a second category |

### Journey B — Consumer (B2C, the data source)

| Stage | Experience |
| --- | --- |
| Discovery | Social media (TikTok/Instagram), university ambassador, mall activation signage |
| Research | App-store listing, friend referral, "what do I get" clarity in onboarding |
| Purchase (of attention, not money) | Consumer never pays — signs up with phone number/OTP |
| Onboarding | Profile setup (age, city, interests) — kept under 60 seconds |
| Usage | Notification of nearby campaign → visit → receive sample → 30-second survey |
| Support | In-app chat for reward/redemption issues |
| Renewal | N/A — replaced by ongoing engagement via new campaign notifications |
| Referral | In-app referral code with bonus points |
| Expansion | Joins interest-based community (Food Lovers, Beauty Lovers, etc.) for more frequent campaigns |

# Phase 6 — Product Ecosystem

### Products

- Sampling Campaigns (core) — physical product trial + structured feedback capture

- AI Insights Dashboard — subscription analytics layer for brand marketing teams

- Consumer Panel Access — sell access to defined demographic/interest segments

- Retail Media — sponsored placement within the app and at physical activation sites

- Enterprise API — CRM/data-warehouse integration for large accounts

### Packages & Pricing (illustrative — pending sprint validation)

| Package | Target | Includes | Illustrative Price |
| --- | --- | --- | --- |
| Starter | Small/challenger brands | 1 campaign, basic dashboard | $4,000–7,000/campaign |
| Growth | Medium FMCG | Multiple campaigns, segmentation | $8,000–14,000/campaign |
| Enterprise | Large accounts | Unlimited campaigns, custom analytics, dedicated CS, AI forecasting, API | $15,000–20,000+/month or custom |

### Product Roadmap

| Version | Scope | Timing (post-GO) |
| --- | --- | --- |
| V1 (Lean MVP) | Admin dashboard, brand dashboard, consumer app, QR validation, 3–5 question survey, basic analytics | Days 1–90 |
| V2 | Gamification, rewards/referral engine, coupon redemption, subscription billing | Months 3–6 |
| V3 | AI insight narratives, predictive purchase-intent scoring, segmentation engine | Months 6–12 |
| V4 | Retail media placements, enterprise API, consumer panel marketplace | Months 12–24 |

### Integrations

- Payment/rewards: Vodafone Cash, InstaPay, bank cards, digital vouchers

- Messaging: WhatsApp Business API for campaign notifications (high Egypt penetration)

- CRM: HubSpot/Salesforce connector for enterprise brand accounts

- Analytics export: CSV/API for brand data teams

### AI Features

- Fraud/bot-response detection on survey submissions

- Auto-generated, plain-language insight narratives (e.g. "Women 22–30 in New Cairo showed 41% higher purchase intent")

- Campaign-targeting recommendation engine (which segments/locations to prioritize)

- Predictive repeat-purchase likelihood scoring

# Phase 7 — Technology Architecture

| Layer | Choice | Rationale |
| --- | --- | --- |
| Consumer frontend | Flutter (single codebase, iOS + Android) | Egypt is mixed iOS/Android; one codebase keeps a 2-engineer team viable in Year 1 |
| Brand dashboard frontend | React / Next.js web app | Brand users are desk-based; a responsive web app avoids a second native build |
| Backend | Node.js/NestJS (API layer) + Python (data/AI services) | NestJS for fast API development; Python for the AI/data-science workloads |
| Primary database | PostgreSQL | Relational integrity for campaigns, users, brands, contracts |
| Cache | Redis | Session state, rate-limiting, fraud-check speed |
| Analytics warehouse | BigQuery or Snowflake | Decouples heavy analytics queries from the transactional database |
| Cloud/hosting | AWS, nearest compliant region (UAE/Bahrain) with data-residency review | AWS has no native Egypt region — data-residency treatment under Law 151/2020 must be confirmed with counsel before go-live |
| Event backbone | Kafka or AWS SQS | Decouples campaign/survey events from real-time dashboard updates as volume grows |
| Authentication | OTP-based phone auth (consumer) + email/SSO (brand dashboard) | Phone-based OTP is the dominant, trusted pattern for Egyptian consumer apps |
| AI layer | OpenAI/Anthropic API for insight-narrative generation; custom-trained model for fraud detection once campaign volume supports it | Buy the general-purpose layer, build the fraud model in-house once there's proprietary data to train on |
| Monitoring | Sentry (errors), Grafana/Prometheus or Datadog (infrastructure) | Standard, cost-appropriate for a Year-1 team |
| Security | Encryption at rest and in transit, role-based access control, quarterly penetration testing, PDPL-compliant data handling and deletion workflows | Non-negotiable per IC Memo's top-rated legal risk (data privacy) |
| Scalability approach | Stateless services behind a load balancer, horizontal autoscaling, queue-based decoupling of fulfillment/survey/analytics workloads | Avoids a rebuild when moving from Cairo-only to multi-city in Year 2 |

# Phase 8 — Business KPIs

| Category | KPIs |
| --- | --- |
| Executive | MRR/ARR, runway (months), sprint-to-GO conversion, brand pipeline value, burn multiple |
| Financial | Gross margin (target ≈60% blended), CAC (consumer <$2, brand $2,000–5,000), LTV, payback period, DSO |
| Marketing | App installs, activation rate, cost per install, community growth by vertical (food/beauty/fitness/etc.) |
| Sales | Pipeline value, win rate, average contract value, sales-cycle length, renewal rate |
| Operations | Fulfillment SLA (48–72 hrs), cost per sample, fraud rate, field-staff utilization |
| Customer | Brand NPS, consumer NPS, survey completion rate (target 80%), MAU, monthly retention |
| AI/Data | Fraud-detection accuracy, insight-generation turnaround time, model drift rate, % campaigns with AI-generated narrative delivered on time |

# Phase 9 — Master Execution Blueprint (Day 1 → Day 730)

| Window | Track | What Happens |
| --- | --- | --- |
| Day 1–60 | Track 0 (funded now) | Validation sprint: 30–50 brand interviews, 5+ LOIs targeted, bottom-up TAM model, Marketeers Research deep-dive, PDPL legal review |
| Day 60 | Gate | IC reviews sprint results against IC Memo §11 Go/No-Go criteria |
| Day 61–150 | Track 1, if GO | Hire core Year-1 team (10–12 people); build Lean MVP (admin + brand dashboard, consumer app, QR, survey, analytics); no AI/ML yet |
| Day 150–210 | Track 1 | First live campaign at 200+ users, 5 brands, 1,000 samples, 80% survey completion target |
| Day 210–365 (6–12 mo) | Track 1 | Scale to 10,000 users / 15 brands / 30 campaigns; add gamification, rewards, referral; launch dashboard subscription; begin Year-2 hiring |
| Year 2 (Day 365–730) | Track 1 | Expand to Alexandria, Giza, New Cairo, 6th October; ship AI insights, segmentation, predictive analytics; reach 100,000 users; build out Marketing, CS, HR, Support departments |
| Year 3 (conditional) | Track 1 | GCC expansion only if Egypt unit economics and retention are proven, per IC Memo scaling gate |

The one rule that governs this whole blueprint • Every hire, every dollar, every department in Track 1 is pre-planned, not pre-authorized. The only currently authorized spend is the Track 0 validation sprint. This document exists so that a GO decision on Day 60 can move to execution on Day 61 with zero planning delay — not so that hiring or spending starts today.