MASTER DELIVERY PLAN

PMO Execution Package v1.0 — MVP Delivery

Tajribti (تجربتي) — Egypt's Consumer Intelligence Platform

| Field | Detail |
| --- | --- |
| Document Type | Master Delivery Plan — 20 PMO deliverables consolidated into one governed package |
| Governed by | IC Memo v1.0, Founder Decisions Document v1.0, Master PRD v1.0, Technical Architecture v1.0 |
| Scope | Sprint 0 through Production (MVP + V1), fully planned; V2/Future release-level only |
| Company | Tajribti (working name) |
| Date | 26 July 2026 |
| Version | 1.0 |

Scope calibration — read first • Full 20-field backlog specification and worked WBS decomposition are provided in complete depth for the 12 features on the MVP critical path (the same set fully specified in the Master PRD). • Remaining MVP/V1 features are backlog-ready (ID, Epic, priority, points, sprint, dependencies) but receive full Definition-of-Ready grooming in the sprint immediately before they are built — standard PMO practice, not a gap. • See Section 18 (Critical Risks Before Development) for the one dependency every plan in this document rests on.

# Table of Contents

# 1. Master Work Breakdown Structure (WBS)

## Decomposition Hierarchy

Programs → Projects → Epics → Features → User Stories → Tasks → Subtasks. No item below the Feature level exceeds one developer-sprint.

| Level | This Project's Instance |
| --- | --- |
| Program | Tajribti Platform (Egypt Launch) |
| Projects | P1 Consumer App · P2 Brand Dashboard · P3 Admin Portal · P4 Platform/Backend · P5 Infrastructure & DevOps · P6 AI Layer (V2) |
| Epics (12) | EPIC-01 Identity & Auth · EPIC-02 Consumer Experience · EPIC-03 Campaign Management · EPIC-04 Fulfillment & Redemption · EPIC-05 Survey & Data Capture · EPIC-06 Analytics & Reporting · EPIC-07 Notifications · EPIC-08 Support · EPIC-09 Consent & Privacy · EPIC-10 Admin/Ops Console · EPIC-11 DevOps & Infra Foundation · EPIC-12 Security Foundation |
| Features | 22 features per Master PRD Phase 3 (e.g. QR Redemption, Campaign Creation Wizard, Basic Analytics Report) |
| User Stories | Per Master PRD Phase 5, plus additional stories generated below for engineering/QA/DevOps work not user-facing |
| Tasks | Sub-feature engineering units (e.g. "Implement QR uniqueness constraint"), sized 0.5–3 days |
| Subtasks | Atomic units within a task (e.g. "Write DB migration for qr_code unique index"), sized hours |

## Worked Example — Full Decomposition of One Feature (Feature 5: QR Redemption)

Shown in full to demonstrate the decomposition standard applied consistently across all 22 features.

| Level | Item |
| --- | --- |
| Epic | EPIC-04 Fulfillment & Redemption |
| Feature | F-05 QR Redemption (P0) |
| User Story | US-05.1: As a consumer at a sampling location, I want to scan a QR code and immediately get my sample, so that I don't have to explain myself to field staff (Master PRD Phase 5) |
| Task 1 | Design and implement QR code generation service (unique per campaign-location-time-window) |
| Subtasks (Task 1) | 1.1 Define QR payload schema · 1.2 Implement generation endpoint · 1.3 Unit test uniqueness collision handling · 1.4 Load-test batch generation for 10,000 codes |
| Task 2 | Implement redemption endpoint with stock/validity checks |
| Subtasks (Task 2) | 2.1 Write DB migration for redemption_event table + qr_code unique index · 2.2 Implement POST /redemptions endpoint · 2.3 Implement stock-depletion check and error response · 2.4 Implement already-redeemed error response · 2.5 Write integration tests for all three outcomes |
| Task 3 | Consumer app — QR scanner screen |
| Subtasks (Task 3) | 3.1 Build camera/scanner UI component · 3.2 Wire scan result to redemption API call · 3.3 Build success/already-used/out-of-stock UI states · 3.4 Implement offline-queue fallback per PRD edge case |
| Task 4 | Field Ops — redemption counter view |
| Subtasks (Task 4) | 4.1 Build real-time stock/redemption counter component · 4.2 Wire to live event stream · 4.3 Low-stock alert trigger |
| Task 5 | QA & Documentation |
| Subtasks (Task 5) | 5.1 Write E2E test (Playwright/Flutter integration_test) · 5.2 Update OpenAPI spec · 5.3 Add ADR if any deviation from Technical Architecture occurred |

## Epic → Feature Summary (all 22 features)

| Epic | Features (PRD #) | Priority Mix |
| --- | --- | --- |
| EPIC-01 Identity & Auth | F-01 OTP Login | P0 |
| EPIC-02 Consumer Experience | F-02 Profile Setup, F-03 Campaign Discovery, F-09 Rewards Wallet, F-10 Referral, F-11 Communities | 3×P0, 2×P1/P2 |
| EPIC-03 Campaign Management | F-13 Campaign Wizard, F-12 Brand Onboarding, F-16 Brand User Mgmt, F-17 Invoice View | 3×P0, 1×P1 |
| EPIC-04 Fulfillment & Redemption | F-05 QR Redemption, F-20 Campaign Config & Approval | 2×P0 |
| EPIC-05 Survey & Data Capture | F-06 Post-Trial Survey | 1×P0 |
| EPIC-06 Analytics & Reporting | F-14 Live Monitoring, F-15 Basic Analytics Report, F-18 AI Insight Narratives | 2×P0, 1×P2 |
| EPIC-07 Notifications | F-04 Push Notification | 1×P0 |
| EPIC-08 Support | F-07 Consumer Support, F-22 Ticket Management (internal) | 2×P0 |
| EPIC-09 Consent & Privacy | F-08 Consent & Privacy Center | 1×P0 — non-negotiable per FDD |
| EPIC-10 Admin/Ops Console | F-21 Fraud Review Queue, F-19 Enterprise API/CRM | 1×P0(manual)/P1(auto), 1×P2 |
| EPIC-11 DevOps & Infra Foundation | Non-PRD engineering epic — see Section 8 | P0, all pre-Sprint-1 |
| EPIC-12 Security Foundation | Non-PRD engineering epic — see Section 11 | P0, all pre-Sprint-1 |

# 2. Product Backlog

Full 20-field specification for the 12 MVP critical-path items. Remaining backlog items follow in summary form.

TJ-001 — OTP Registration/Login

| Field | Value |
| --- | --- |
| Epic | EPIC-01 |
| Feature | F-01 |
| Priority | P0 |
| Business Value | High — no consumer funnel exists without this |
| Technical Complexity | Medium (SMS provider integration, rate limiting) |
| Story Points | 5 |
| Estimated Hours | 24h |
| Owner | Backend Eng 1 + Mobile Eng |
| Dependencies | SMS/OTP provider contract signed (Sprint 0) |
| Acceptance Criteria | Per Master PRD Feature 1 AC (4 criteria) |
| Definition of Done | Code merged, unit+integration tests passing, OpenAPI updated, deployed to staging, demoed |
| Definition of Ready | SMS provider sandbox credentials available; UX mockup approved |
| Risk Level | Medium — SMS deliverability on Egyptian carriers unverified until Sprint 0 spike |
| Release Version | MVP |
| Sprint Assignment | Sprint 1 |
| Testing Requirements | Unit, integration, manual test on 3 carriers |
| Documentation Requirements | API docs, runbook for OTP provider outage |
| Deployment Requirements | Secrets Manager entry for provider API key |

TJ-002 — Consumer Profile Setup

| Field | Value |
| --- | --- |
| Epic | EPIC-02 |
| Feature | F-02 |
| Priority | P0 |
| Business Value | High — enables all targeting/segmentation |
| Technical Complexity | Low |
| Story Points | 3 |
| Estimated Hours | 14h |
| Owner | Mobile Eng |
| Dependencies | TJ-001 |
| Acceptance Criteria | Per Master PRD Feature 2 AC |
| Definition of Done | Merged, tested, staging-deployed, demoed |
| Definition of Ready | Field list and consent copy legally reviewed |
| Risk Level | Low |
| Release Version | MVP |
| Sprint Assignment | Sprint 1 |
| Testing Requirements | Unit, integration |
| Documentation Requirements | Data-dictionary entry |
| Deployment Requirements | None beyond standard pipeline |

TJ-005 — QR Redemption

| Field | Value |
| --- | --- |
| Epic | EPIC-04 |
| Feature | F-05 |
| Priority | P0 |
| Business Value | Critical — the fraud-control point of the entire product |
| Technical Complexity | High (uniqueness guarantees, offline queue, concurrency at high-traffic locations) |
| Story Points | 13 |
| Estimated Hours | 56h |
| Owner | Backend Eng 2 + Mobile Eng |
| Dependencies | TJ-020 (Campaign Config & Approval, for QR batch source) |
| Acceptance Criteria | Per Master PRD Feature 5 AC (3 criteria) + WBS Task breakdown (Section 1) |
| Definition of Done | Load-tested to 50 concurrent redemptions/location, merged, demoed |
| Definition of Ready | Campaign Config feature reaches "QR batch generated" state in staging |
| Risk Level | High — concurrency bugs here directly corrupt brand-facing data quality |
| Release Version | MVP |
| Sprint Assignment | Sprint 2 |
| Testing Requirements | Unit, integration, load test, offline-sync manual test |
| Documentation Requirements | Runbook: QR dispute resolution for field staff |
| Deployment Requirements | Feature-flagged rollout |

TJ-006 — Post-Trial Survey

| Field | Value |
| --- | --- |
| Epic | EPIC-05 |
| Feature | F-06 |
| Priority | P0 |
| Business Value | Critical — this is the product |
| Technical Complexity | Medium |
| Story Points | 8 |
| Estimated Hours | 36h |
| Owner | Backend Eng 1 + Mobile Eng |
| Dependencies | TJ-005 |
| Acceptance Criteria | Per Master PRD Feature 6 AC |
| Definition of Done | Merged, tested, demoed with a real 5-question campaign |
| Definition of Ready | Survey schema data model finalized (depends on TJ-013) |
| Risk Level | Medium — abandonment-rate handling needs product sign-off before build |
| Release Version | MVP |
| Sprint Assignment | Sprint 2 |
| Testing Requirements | Unit, integration, A/B test harness for question count |
| Documentation Requirements | Analytics event dictionary |
| Deployment Requirements | None beyond standard pipeline |

TJ-004 — Push Notification — New Campaign

| Field | Value |
| --- | --- |
| Epic | EPIC-07 |
| Feature | F-04 |
| Priority | P0 |
| Business Value | High — primary redemption-volume driver |
| Technical Complexity | Medium (targeting logic, frequency capping) |
| Story Points | 8 |
| Estimated Hours | 32h |
| Owner | Backend Eng 2 |
| Dependencies | TJ-002, TJ-013 |
| Acceptance Criteria | Per Master PRD Feature 4 AC |
| Definition of Done | Merged, tested against 2+ overlapping campaigns without duplicate spam, demoed |
| Definition of Ready | Push provider (FCM/APNs) and WhatsApp BSP contracts active |
| Risk Level | Medium — WhatsApp BSP approval timelines are outside engineering's control |
| Release Version | MVP |
| Sprint Assignment | Sprint 3 |
| Testing Requirements | Unit, integration, manual multi-campaign overlap test |
| Documentation Requirements | Runbook: notification-provider outage fallback |
| Deployment Requirements | Secrets for FCM/APNs/WhatsApp BSP |

TJ-008 — Consent & Privacy Center

| Field | Value |
| --- | --- |
| Epic | EPIC-09 |
| Feature | F-08 |
| Priority | P0 |
| Business Value | Critical — FDD non-negotiable, removes top legal risk |
| Technical Complexity | Medium (data export, cross-table anonymization on deletion) |
| Story Points | 8 |
| Estimated Hours | 36h |
| Owner | Backend Eng 1 |
| Dependencies | Legal sign-off on deletion SLA (Sprint 0) |
| Acceptance Criteria | Per Master PRD Feature 8 AC |
| Definition of Done | Legal-reviewed, merged, tested, demoed with a full delete-and-verify cycle |
| Definition of Ready | Counsel confirms PDPL deletion-timeframe requirement |
| Risk Level | High — cannot launch MVP without this; legal dependency, not engineering |
| Release Version | MVP |
| Sprint Assignment | Sprint 1 (start), Sprint 3 (complete) |
| Testing Requirements | Unit, integration, manual legal-acceptance test |
| Documentation Requirements | PDPL compliance evidence pack |
| Deployment Requirements | None beyond standard pipeline |

TJ-013 — Campaign Creation Wizard

| Field | Value |
| --- | --- |
| Epic | EPIC-03 |
| Feature | F-13 |
| Priority | P0 |
| Business Value | Critical — the revenue-triggering event |
| Technical Complexity | Medium-High (state machine, validation, low-reach warning logic) |
| Story Points | 13 |
| Estimated Hours | 52h |
| Owner | Frontend Eng (Next.js) + Backend Eng 2 |
| Dependencies | TJ-012 (Brand Onboarding) |
| Acceptance Criteria | Per Master PRD Feature 13 AC |
| Definition of Done | Merged, tested, demoed end-to-end from submission to Ops queue |
| Definition of Ready | Campaign state machine confirmed against Technical Architecture Phase 4 |
| Risk Level | Medium |
| Release Version | MVP |
| Sprint Assignment | Sprint 2–3 |
| Testing Requirements | Unit, integration, E2E (Playwright) |
| Documentation Requirements | Brand-facing help copy |
| Deployment Requirements | None beyond standard pipeline |

TJ-014 — Live Campaign Monitoring

| Field | Value |
| --- | --- |
| Epic | EPIC-06 |
| Feature | F-14 |
| Priority | P0 |
| Business Value | High — drives renewal by showing value mid-campaign |
| Technical Complexity | Medium (near-real-time data via SQS events) |
| Story Points | 8 |
| Estimated Hours | 32h |
| Owner | Frontend Eng (Next.js) + Backend Eng 1 |
| Dependencies | TJ-005, TJ-006 |
| Acceptance Criteria | Per Master PRD Feature 14 AC |
| Definition of Done | Merged, tested, sub-5-minute data latency confirmed, demoed |
| Definition of Ready | SQS event schema finalized |
| Risk Level | Low |
| Release Version | MVP |
| Sprint Assignment | Sprint 4 |
| Testing Requirements | Unit, integration, latency test |
| Documentation Requirements | None beyond OpenAPI |
| Deployment Requirements | None beyond standard pipeline |

TJ-015 — Basic Analytics Report + CSV Export

| Field | Value |
| --- | --- |
| Epic | EPIC-06 |
| Feature | F-15 |
| Priority | P0 |
| Business Value | Critical — the deliverable brands are paying for |
| Technical Complexity | Medium (PII exclusion logic, low-confidence-segment flagging) |
| Story Points | 8 |
| Estimated Hours | 36h |
| Owner | Backend Eng 2 |
| Dependencies | TJ-006 |
| Acceptance Criteria | Per Master PRD Feature 15 AC |
| Definition of Done | Merged, privacy-reviewed, tested, demoed on a completed pilot campaign |
| Definition of Ready | Privacy review of export format complete |
| Risk Level | Medium — data-quality bugs here directly damage brand trust |
| Release Version | MVP |
| Sprint Assignment | Sprint 4 |
| Testing Requirements | Unit, integration, privacy-compliance manual test |
| Documentation Requirements | Report methodology one-pager for brand clients |
| Deployment Requirements | None beyond standard pipeline |

TJ-020 — Campaign Configuration & Approval (Admin)

| Field | Value |
| --- | --- |
| Epic | EPIC-04 |
| Feature | F-20 |
| Priority | P0 |
| Business Value | Critical — controls fulfillment SLA achievability |
| Technical Complexity | Medium-High (multi-location assignment logic) |
| Story Points | 13 |
| Estimated Hours | 48h |
| Owner | Backend Eng 1 + Frontend Eng |
| Dependencies | TJ-013 |
| Acceptance Criteria | Per Master PRD Feature 20 AC |
| Definition of Done | Merged, tested against a 3+ location campaign, demoed |
| Definition of Ready | Retail-partner location data model finalized |
| Risk Level | Medium |
| Release Version | MVP |
| Sprint Assignment | Sprint 2 |
| Testing Requirements | Unit, integration, multi-location E2E |
| Documentation Requirements | Ops runbook for manual override |
| Deployment Requirements | None beyond standard pipeline |

TJ-012 — Brand Account Onboarding (Sales-assisted)

| Field | Value |
| --- | --- |
| Epic | EPIC-03 |
| Feature | F-12 |
| Priority | P0 |
| Business Value | High — gate to all brand-side revenue |
| Technical Complexity | Low |
| Story Points | 5 |
| Estimated Hours | 20h |
| Owner | Backend Eng 2 |
| Dependencies | TJ-001 (auth foundation) |
| Acceptance Criteria | Per Master PRD Feature 12 (implicit AC: invite flow, first-login) |
| Definition of Done | Merged, tested, demoed with a real internal test brand account |
| Definition of Ready | Email invite copy approved |
| Risk Level | Low |
| Release Version | MVP |
| Sprint Assignment | Sprint 1 |
| Testing Requirements | Unit, integration |
| Documentation Requirements | CS runbook for manual account creation |
| Deployment Requirements | SES/SendGrid configured |

TJ-022 — Support Ticket Management (Internal)

| Field | Value |
| --- | --- |
| Epic | EPIC-08 |
| Feature | F-22 |
| Priority | P0 |
| Business Value | Medium — required before any real users touch the product |
| Technical Complexity | Low-Medium |
| Story Points | 5 |
| Estimated Hours | 22h |
| Owner | Backend Eng 2 + Frontend Eng |
| Dependencies | TJ-007 (Consumer Support submission) |
| Acceptance Criteria | Ticket create/triage/resolve/escalate flow functions per Master PRD Support process |
| Definition of Done | Merged, tested, demoed with a simulated ticket |
| Definition of Ready | Support Agent role permissions finalized |
| Risk Level | Low |
| Release Version | MVP |
| Sprint Assignment | Sprint 4 |
| Testing Requirements | Unit, integration |
| Documentation Requirements | Support Agent onboarding guide |
| Deployment Requirements | None beyond standard pipeline |

## Remaining Backlog (Summary Form)

Groomed to full 20-field detail one sprint before build, per FDD Budget Philosophy ("no headcount/work committed before it's needed").

| ID | Title | Priority | Points | Sprint | Dependencies |
| --- | --- | --- | --- | --- | --- |
| TJ-003 | Campaign Discovery (list/map) | P0 | 5 | Sprint 3 | TJ-002, TJ-013 |
| TJ-007 | In-App Consumer Support | P0 | 5 | Sprint 4 | TJ-001 |
| TJ-016 | Brand User Management | P0 | 3 | Sprint 3 | TJ-012 |
| TJ-021 | Fraud Review Queue (manual) | P0 | 5 | Sprint 4 | TJ-006 |
| TJ-009 | Rewards Wallet | P1 | 13 | V1 Sprint 1 | TJ-002, Payment integration |
| TJ-010 | Referral Program | P1 | 8 | V1 Sprint 2 | TJ-009 |
| TJ-017 | Contract & Invoice View | P1 | 5 | V1 Sprint 1 | Finance manual process |
| TJ-021b | Automated Fraud Detection Model | P1 | 13 | V1 Sprint 3 | TJ-021, real campaign data |
| TJ-011 | Interest-Based Communities | P2 | 8 | V2 | TJ-003 |
| TJ-018 | AI Insight Narratives | P2 | 13 | V2 | AI Gateway (Technical Architecture Phase 7) |
| TJ-019 | Enterprise API / CRM Connector | P2 | 13 | V2 | TJ-015 |

# 3. Sprint Backlog

Two-week sprints. Sprint 0 (setup) + Sprints 1–4 reach MVP (8 weeks engineering + buffer = the PRD's Day 61–150 window). Sprints 5–6 cover hardening/beta before Production.

Sprint 0 — Setup (2 wks)

| Field | Detail |
| --- | --- |
| Sprint Goal | Engineering environment and foundations ready — zero product code required to demo |
| Deliverables | Repo scaffolded, CI/CD pipeline green, staging environment live, SMS/OTP + WhatsApp BSP + payment provider contracts signed, PDPL legal review kicked off, design system v0 |
| Included Stories | N/A — no user stories; infra/EPIC-11/EPIC-12 tasks only |
| Capacity | 5 engineers (per Blueprint Year-1 team) |
| Risks | Provider contract delays (WhatsApp BSP approval can take weeks) — start Sprint 0 in parallel with Track 0 validation sprint, not after it |
| Dependencies | None (first sprint) |
| Expected Demo | Working CI/CD pipeline deploying a hello-world service to staging |
| Definition of Done | All infra provisioned, all third-party accounts active, legal kickoff meeting held |
| Go/No-Go | GO if: staging environment reachable, at least 2 of 3 external contracts (SMS, WhatsApp, payment) signed |

Sprint 1 (2 wks)

| Field | Detail |
| --- | --- |
| Sprint Goal | Consumer can register and a brand account can exist |
| Deliverables | TJ-001 OTP Login, TJ-002 Profile Setup, TJ-012 Brand Onboarding, TJ-008 Consent Center (start) |
| Included Stories | TJ-001, TJ-002, TJ-012, TJ-008 (partial) |
| Capacity | 5 engineers, ~200h capacity |
| Risks | SMS deliverability on Egyptian carriers unverified — Sprint 0 spike should have de-risked this |
| Dependencies | Sprint 0 infra complete |
| Expected Demo | A real phone number completes OTP signup end-to-end |
| Definition of Done | All Sprint 1 stories meet Definition of Done |
| Go/No-Go | GO if: OTP success rate ≥95% in staging test across 3 carriers |

Sprint 2 (2 wks)

| Field | Detail |
| --- | --- |
| Sprint Goal | A brand can create a campaign and a consumer can redeem a sample |
| Deliverables | TJ-013 Campaign Wizard, TJ-020 Campaign Config/Approval, TJ-005 QR Redemption, TJ-006 Survey (start) |
| Included Stories | TJ-013, TJ-020, TJ-005, TJ-006 (partial) |
| Capacity | 5 engineers, ~200h capacity |
| Risks | QR concurrency bugs are the highest-severity technical risk in the whole MVP — allocate extra QA time here |
| Dependencies | Sprint 1 complete (Auth, Brand accounts) |
| Expected Demo | Full campaign creation → QR redemption loop (no survey yet) |
| Definition of Done | All Sprint 2 stories meet DoD, QR load test passed |
| Go/No-Go | GO if: 50 concurrent redemptions handled with zero data corruption |

Sprint 3 (2 wks)

| Field | Detail |
| --- | --- |
| Sprint Goal | The core data loop closes — redemption feeds a survey feeds notifications |
| Deliverables | TJ-006 (complete), TJ-004 Push Notification, TJ-003 Campaign Discovery, TJ-016 Brand User Mgmt, TJ-008 (complete) |
| Included Stories | TJ-006, TJ-004, TJ-003, TJ-016, TJ-008 |
| Capacity | 5 engineers, ~200h capacity |
| Risks | WhatsApp BSP approval may still be pending — fallback to push-only notification if so |
| Dependencies | Sprint 2 complete |
| Expected Demo | Consumer discovers a campaign, redeems, completes survey; brand sees it happen live (pre-dashboard) |
| Definition of Done | All Sprint 3 stories meet DoD, PDPL legal sign-off obtained for TJ-008 |
| Go/No-Go | GO if: legal sign-off received — this is a hard gate, not negotiable |

Sprint 4 (2 wks)

| Field | Detail |
| --- | --- |
| Sprint Goal | Brands can see and export what they paid for |
| Deliverables | TJ-014 Live Monitoring, TJ-015 Analytics Report, TJ-007 Consumer Support, TJ-021 Fraud Review Queue, TJ-022 Support Tickets |
| Included Stories | TJ-014, TJ-015, TJ-007, TJ-021, TJ-022 |
| Capacity | 5 engineers, ~200h capacity |
| Risks | Data-quality bugs in the analytics report directly damage brand trust — full QA pass before demo |
| Dependencies | Sprint 3 complete |
| Expected Demo | A full simulated campaign lifecycle, ending in a brand downloading a CSV report |
| Definition of Done | All Sprint 4 stories meet DoD |
| Go/No-Go | GO if: a full end-to-end pilot campaign (internal test brand + test consumers) completes cleanly |

Sprint 5 — Hardening (2 wks)

| Field | Detail |
| --- | --- |
| Sprint Goal | MVP is feature-complete; this sprint is bug-fixing, performance, and security only |
| Deliverables | Load testing, penetration-test remediation, accessibility pass, Arabic-copy QA, monitoring/alerting finalization |
| Included Stories | No new features — bug-fix backlog only |
| Capacity | 5 engineers, ~200h capacity |
| Risks | Scope creep — Product must hold the line on "no new features in hardening" |
| Dependencies | Sprint 4 complete, feature-complete build |
| Expected Demo | Internal Alpha demo to the full founding team + IC |
| Definition of Done | Zero P0/P1 bugs open, penetration-test findings triaged |
| Go/No-Go | GO if: zero P0 security findings remain open |

Sprint 6 — Private Beta Prep (2 wks)

| Field | Detail |
| --- | --- |
| Sprint Goal | Ready to onboard the first 5 real brand pilots (the sprint's own LOI targets) |
| Deliverables | Onboard 5 real brand accounts, run first real campaigns, support/ops runbooks finalized |
| Included Stories | Real-world validation, not new stories |
| Capacity | 5 engineers + Ops/Support live |
| Risks | Real brands may surface requirements gaps the simulated pilots didn't — budget slack for fast-follow fixes |
| Dependencies | Sprint 5 complete, all P0 bugs closed |
| Expected Demo | A live campaign running with a real brand client |
| Definition of Done | Private Beta success criteria met (Section 4) |
| Go/No-Go | GO if: Private Beta entry criteria (Section 4) are met |

# 4. Release Roadmap

| Release | Objectives | Features | Entry Criteria | Exit Criteria | Testing Scope | Rollback Plan |
| --- | --- | --- | --- | --- | --- | --- |
| Internal Alpha | Validate the full loop works with the founding team only | MVP feature set, no real brands/consumers | Sprint 5 hardening complete | Zero P0 bugs, all demos pass | Full regression + security | N/A — internal only, no rollback needed |
| Private Beta | Validate with 5 real brand pilots from the LOI list | MVP feature set | Internal Alpha exit criteria met + 5 signed brand pilots | ≥3 of 5 pilot brands complete a full campaign successfully; survey completion ≥70% | Full regression + real-user UAT | Feature-flag disable per brand; database rollback plan documented and tested |
| Public Beta | Open registration to consumers (brands remain invite-only) | MVP feature set + Rewards Wallet (TJ-009) if V1 Sprint 1 is complete | Private Beta exit criteria met, ≥80% survey completion sustained | App-store approval obtained; support SLA holding at scale | Load test at 10x Private Beta volume | Kill-switch on new consumer registration; existing users unaffected |
| Release Candidate | Final production-readiness gate | Public Beta feature set, frozen | Public Beta stable for 2 weeks with no P0/P1 bugs | Sign-off from CEO, CTO, and Legal (per FDD) | Full regression, penetration test, accessibility audit | Standard ECS rollback to last known-good task definition |
| Production (v1.0) | Full public launch | MVP + any V1 items completed during Beta | RC sign-off obtained | Meets Section 14 success metrics for 30 days | Ongoing monitoring, no additional test cycle | Documented in Go-Live Plan (Section 14) |
| v1.1 | First iteration post-launch — Rewards, Referral, Contract self-view | TJ-009, TJ-010, TJ-017, automated fraud model (TJ-021b) | v1.0 stable for 30 days | Feature-specific UAT per item | Standard regression + new-feature UAT | Feature-flagged, independently rollback-able per feature |
| v2.0 | AI Insight Narratives, Enterprise API, predictive analytics | TJ-018, TJ-019, segmentation engine | Egypt unit economics validated per FDD scaling gate | AI output accuracy/safety review passed (Section 12) | AI-specific evaluation suite + standard regression | AI features flagged off independently; core product unaffected by AI rollback |

# 5. Dependency Matrix

| Upstream | Downstream | Type | Risk if Delayed |
| --- | --- | --- | --- |
| Track 0 validation sprint GO decision | Everything in this document | Hard gate | Entire plan does not start — see Section 18 |
| SMS/OTP provider contract | TJ-001 OTP Login | External | Sprint 1 cannot demo; cascades to all consumer-side work |
| WhatsApp BSP approval | TJ-004 Push Notification (WhatsApp channel) | External | Fallback to push-only; not launch-blocking but reduces reach |
| PDPL legal sign-off | TJ-008 Consent & Privacy Center | Legal | Hard gate — MVP cannot launch without this per FDD non-negotiable |
| TJ-020 Campaign Config | TJ-005 QR Redemption | Internal engineering | QR batches have no source; blocks Sprint 2 demo |
| TJ-005 QR Redemption | TJ-006 Post-Trial Survey | Internal engineering | Survey cannot trigger without a redemption event |
| TJ-006 Post-Trial Survey | TJ-014 Live Monitoring, TJ-015 Analytics Report | Internal engineering | No data to display or export |
| Retail-partner location agreements (Ops/Sales) | TJ-020 Campaign Config | Business/external | No physical locations to configure campaigns against |
| AWS region / data-residency legal confirmation | All infrastructure provisioning | Legal + infra | Sprint 0 cannot finalize hosting region — open FDD decision |

# 6. Risk Register

| ID | Risk | Category | Probability | Impact | Owner | Mitigation |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Validation sprint gate not yet confirmed passed | Programmatic | Confirmed as current state | Critical — blocks everything | CEO/IC | See Section 18 — this is the plan's actual current status, not a future risk |
| R-02 | SMS OTP deliverability fails on a major Egyptian carrier | Technical | Medium | High | Backend Eng | Sprint 0 spike tests all 3 major carriers before Sprint 1 commitment |
| R-03 | QR redemption concurrency bug corrupts data at a high-traffic location | Technical | Medium | Critical | Backend Eng | Load testing mandatory before Sprint 2 exit; feature-flagged rollout |
| R-04 | PDPL legal sign-off delayed beyond Sprint 3 | Legal | Medium | Critical | Legal/CEO | Kicked off in Sprint 0, in parallel with engineering, not after |
| R-05 | WhatsApp BSP approval delayed | External/Vendor | Medium | Medium | Ops | Push-notification fallback; not launch-blocking |
| R-06 | Retail-partner locations not secured in time for Sprint 2 demo | Business | Medium | High | Sales/Ops | Begin partner outreach in Track 0/Sprint 0, not Sprint 2 |
| R-07 | Team of 5 engineers is understaffed for the Sprint 1–4 scope as estimated | Resourcing | Medium | High | CTO/PMO | Sprint 1 velocity check-in; scope-cut candidates pre-identified (TJ-016, TJ-022 can slip to Sprint 5 buffer) |
| R-08 | Marketeers Research (identified competitor) launches a competing feature during MVP build | Market | Low-Medium | Medium | CEO | No engineering mitigation — monitor via Sales; differentiate on sampling-to-data pipeline per FDD positioning |
| R-09 | AWS data-residency legal question unresolved, blocking Sprint 0 region finalization | Legal/Infra | Medium | High | Legal/CTO | Escalate as a Sprint 0 Day 1 blocker, not a background task |

# 7. Project Timeline

| Phase | Duration | Window (from Sprint 0 start) |
| --- | --- | --- |
| Sprint 0 — Setup | 2 weeks | Weeks 1–2 |
| Sprints 1–4 — MVP Build | 8 weeks | Weeks 3–10 |
| Sprint 5 — Hardening | 2 weeks | Weeks 11–12 |
| Sprint 6 — Private Beta Prep | 2 weeks | Weeks 13–14 |
| Private Beta | 2–4 weeks (variable, exit-criteria gated) | Weeks 15–18 |
| Public Beta | 2–4 weeks (variable) | Weeks 19–22 |
| Release Candidate + Production | 2 weeks | Weeks 23–24 |

Total: approximately 24 weeks (~6 months) from Sprint 0 start to Production v1.0 — consistent with the 6–12 month horizon in the Master Execution Blueprint. Critical path: Sprint 0 legal/infra → Sprint 1 Auth → Sprint 2 Campaign+QR → Sprint 3 Survey+Notification → Sprint 4 Analytics → Hardening → Beta gates → Production.

# 8. Resource Plan

Reuses the Year-1 team from the Master Execution Blueprint, allocated to sprint capacity.

| Role | Count | Sprint 0–6 Allocation |
| --- | --- | --- |
| CTO | 1 | Architecture ownership, code review, Sprint 2 QR redemption (highest-risk item) |
| Backend Engineer | 2 | Split across Auth/Campaign/Fulfillment (Eng 1) and Survey/Analytics/Notification (Eng 2) |
| Mobile Engineer (Flutter) | 1 | Consumer app — all consumer-facing stories |
| Frontend Engineer (Next.js) | 1 | Brand dashboard + Admin portal |
| Product Manager / CEO (dual role, Y1) | 1 | Backlog grooming, sprint demos, brand pilot relationships |
| Ops Manager | 1 | Retail-partner agreements, field-staff coordination for Private Beta |
| Fractional Legal Counsel | External | PDPL sign-off (Sprint 0–3), contract review |
| Fractional QA | 0.5 FTE from Sprint 2 | Load testing, security test coordination, UAT facilitation |

# 9. QA Master Plan

## Test Strategy

Shift-left: unit and integration tests are written alongside feature code, not after. E2E and performance tests target the critical path defined in the Master PRD. No feature reaches "Done" without its Definition of Done testing requirements met (Section 2).

| Test Type | Scope | Tooling | When |
| --- | --- | --- | --- |
| Unit | Business logic in every module | Jest (Node/React), Flutter test, Pytest (AI service) | Every PR |
| Integration | API endpoints against test DB | Jest + Testcontainers | Every PR |
| API | Full request/response contract per OpenAPI spec | Postman/Newman or Jest+Supertest | Every PR, full suite nightly |
| UI | Component rendering, RTL/Arabic layout correctness | React Testing Library, Flutter widget tests | Every PR |
| Regression | Full critical-path suite | Playwright (web), Flutter integration_test (mobile) | Nightly + before every release gate |
| Performance | API p95 targets, QR redemption concurrency | k6 or Artillery load testing | Before Sprint 2 exit, before every release gate |
| Security | OWASP Top 10, auth/authz bypass attempts | OWASP ZAP automated scan + manual pentest (Sprint 5, quarterly thereafter) | Sprint 5, quarterly |
| Acceptance | Against each backlog item's Acceptance Criteria | Manual, Product-led | Before marking any story Done |
| Smoke | Critical path only, post-deploy | Automated script, <5 min runtime | Every production deploy |
| UAT | Real brand pilots using the actual product | Manual, brand-facing | Private Beta |

## Bug Severity Matrix

| Severity | Definition | Response SLA |
| --- | --- | --- |
| P0 / Blocker | Data corruption, security breach, core loop broken (e.g. redemption fails entirely) | Immediate — halts release |
| P1 / Critical | Major feature broken but workaround exists | Fixed before next release gate |
| P2 / Major | Feature degraded, non-blocking | Fixed within the current release cycle |
| P3 / Minor | Cosmetic, low-impact | Backlogged, fixed opportunistically |

## Exit Criteria (per release gate)

Zero open P0/P1 bugs; all Section 9 test types passed for in-scope features; UAT sign-off (Beta stages); security scan findings triaged (Hardening onward).

# 10. DevOps Plan

| Area | Decision |
| --- | --- |
| Repository | Monorepo (Nx/Turborepo) — consumer-app, brand-dashboard, admin-portal, backend-api, ai-service, shared packages (per Technical Architecture Phase 10) |
| Branch strategy | Trunk-based development; short-lived feature branches (<3 days); PR required for all merges to main |
| CI/CD | GitHub Actions — lint/test/build on every PR; auto-deploy to staging on merge to main; manual approval gate to production |
| Secrets | AWS Secrets Manager; zero secrets in source control; rotated quarterly |
| Monitoring | CloudWatch (infra) + Grafana/Prometheus (application metrics) + Sentry (error tracking) |
| Logging | Structured JSON logs → CloudWatch Logs, correlation IDs on every request for cross-service tracing |
| Alerts | PagerDuty (or equivalent) for P0/P1 alerts — API error-rate spike, QR redemption failure rate, DB connection exhaustion |
| Infrastructure | Terraform, one module per environment, reviewed via PR like application code |
| Containers | Docker images for all services; ECS Fargate task definitions versioned alongside code |
| Scaling | ECS service autoscaling on CPU/memory/request-count; Redis and RDS scaled manually until volume justifies automation |
| Backup | RDS automated daily snapshots, 7-day PITR minimum; weekly cross-region replication |
| Disaster Recovery | RTO 4hrs / RPO 1hr at MVP (Technical Architecture Phase 9); quarterly restore drills |
| Rollback | ECS task-definition revert for application rollback; feature flags for instant feature-level disable without a deploy |
| Observability | Distributed tracing via correlation IDs; dashboards per module (Auth, Fulfillment, Survey) tied to the KPIs in the FDD/PRD |

# 11. Security Plan — Implementation Tasks

| Area | Implementation Task | Backlog Link |
| --- | --- | --- |
| Authentication | OTP rate limiting (3/10min), JWT short-lived access tokens, mandatory internal 2FA | TJ-001, EPIC-12 |
| Authorization | RBAC via NestJS Guards + CASL mapped to PRD Permissions Matrix | EPIC-12 (Sprint 0) |
| Encryption | TLS 1.2+ everywhere; AES-256 at rest; KMS envelope encryption for phone-number field | EPIC-12 (Sprint 0) |
| Audit Logs | Immutable AuditLog table on every Consumer/SurveyResponse write; CloudTrail for infra actions | EPIC-12 (Sprint 0) |
| OWASP | Input validation (class-validator), parameterized queries (ORM default), CSRF protection, CSP headers, Dependabot/Snyk in CI | Sprint 0 + ongoing |
| Rate Limiting | NestJS throttler guard on all public endpoints, stricter limits on OTP/auth endpoints | EPIC-12 (Sprint 0) |
| API Security | OpenAPI-enforced request schemas, no over-fetching, versioned deprecation policy | Sprint 0 + ongoing |
| Data Protection | Minimum-necessary data collection enforced at schema level (no field without a named PRD requirement) | Data model, Sprint 0 |
| Privacy Compliance | PDPL sign-off gate on TJ-008 before MVP launch; self-service deletion live at launch, not deferred | TJ-008 |
| Secrets Management | AWS Secrets Manager, quarterly rotation, zero secrets in source control | EPIC-11 (Sprint 0) |

# 12. AI Implementation Plan (V2 — not MVP)

Scope reminder • Per the FDD and Master PRD, AI is explicitly out of MVP/V1 scope. This plan exists so V2 engineering can begin without re-planning once the Egypt unit-economics gate is cleared.

| Component | Plan |
| --- | --- |
| Prompt Library | Versioned prompt templates in a dedicated module, JSON-mode structured outputs, one template per insight-narrative type (segment comparison, purchase-intent summary) |
| Model Routing | AI Gateway service routes by task type/cost/latency across OpenAI and Anthropic; no hardcoded single-provider calls anywhere in application code |
| Fallback Strategy | Automatic failover to secondary provider on primary error/rate-limit; degraded-mode response (raw data only, no narrative) if both providers fail |
| RAG | Not built for V2 — deferred to a Future "ask your data" conversational feature only if validated as a real need |
| Embeddings / Vector DB | Not built for V2 — same rationale as RAG |
| Knowledge Base | Analytics warehouse (BigQuery/Snowflake) is the source of truth; no separate KB |
| Evaluation | Golden-set evaluation: a fixed set of historical campaign datasets with human-reviewed "correct" narratives, regression-tested against every prompt-template change |
| Prompt Versioning | Every prompt template versioned in source control; A/B capability to compare narrative quality across versions before full rollout |
| Caching | Cache repeated/near-identical insight requests; TTL tied to campaign data freshness |
| Cost Monitoring | Token-usage dashboard tied to Finance KPIs (FDD Budget Philosophy); per-brand-account cost attribution |
| Safety | No insight narrative ships without a sample-size/confidence disclaimer, per FDD Communication Principles — enforced at the template level, not left to model discretion |
| Hallucination Detection | Narrative claims are grounded by construction — the prompt only receives the campaign's actual structured data, with explicit instruction to state "insufficient data" rather than infer beyond the sample; evaluation suite includes adversarial low-sample-size test cases |

# 13. Operational Readiness Plan

## Runbooks (required before Private Beta)

- OTP/SMS provider outage — fallback and consumer communication steps.

- QR dispute resolution for field staff (already-redeemed complaints).

- Notification-provider (WhatsApp/push) outage fallback.

- Manual brand account creation (CS runbook, pre-self-serve).

- PDPL data-deletion request handling and verification.

## Playbooks

- P0 incident response (data corruption, security breach, core-loop outage).

- Fraud-spike response (Fraud Review Queue escalation).

- Campaign fulfillment failure (stock/location issue) response.

## Incident Management

Severity levels match the Bug Severity Matrix (Section 9). P0 incidents trigger immediate CEO/CTO/Legal notification per FDD escalation rule. Post-incident, a blameless retrospective is logged in the Lessons Learned template (Section 15).

## Support & Maintenance Procedures

Consumer support: in-app ticket, <4hr response / <24hr resolution SLA (per PRD). Brand support: dedicated CS contact, relationship-based (per FDD, not ticket-queue). Maintenance windows: scheduled outside Egypt peak usage hours, communicated 48hrs in advance.

## Escalation Matrix

| Severity | First Responder | Escalates To | Timeframe |
| --- | --- | --- | --- |
| P0 | On-call engineer | CTO + CEO | Immediate |
| P1 | On-call engineer | Backend/Frontend lead | Within 2 hours |
| P2 | Support Agent / assigned engineer | Team lead | Within 1 business day |
| P3 | Support Agent | Backlog | Next sprint planning |

## SLAs & Operational KPIs

Reused directly from Master PRD Phase 8: fulfillment SLA 48–72hrs, consumer support response <4hrs/resolution <24hrs, uptime 99.5% (MVP), survey completion ≥80%.

# 14. Go-Live Plan

### Go-Live Checklist

- RC exit criteria met (Section 4).

- CEO, CTO, and Legal sign-off obtained (FDD requirement).

- Production infrastructure provisioned and load-tested.

- On-call rotation scheduled for launch week.

- Rollback plan tested in staging within the prior 7 days.

### Launch Checklist

- DNS cutover plan confirmed.

- App-store listings approved and live.

- Brand pilot accounts migrated from Beta to Production.

- Support team briefed and staffed for launch-week volume.

### Rollback Checklist

- ECS task-definition revert tested.

- Database migration rollback script verified (or confirmed additive-only, no rollback needed).

- Feature-flag kill-switches verified for every new v1.0 feature.

### Production Validation

- Smoke test suite green post-deploy.

- First 10 real redemptions manually spot-checked for data integrity.

- Monitoring dashboards confirmed receiving live data.

### Monitoring Checklist

- Alert thresholds active for API error rate, QR redemption failure rate, DB connection pool, SMS/WhatsApp delivery failure rate.

- On-call engineer has dashboard access confirmed.

### Customer Support Checklist

- Support Agent runbooks published.

- Escalation matrix (Section 13) distributed to all support staff.

### Marketing Launch Checklist

Out of engineering/PMO scope — owned by Marketing per FDD Marketing Strategy; flagged here only as a dependency: consumer acquisition channels (TikTok/Instagram/university ambassadors) must be ready to activate the same week as Production go-live, or early redemption volume will be too low to demonstrate value to Private Beta brands.

### Sales Enablement Checklist

- Case study from Private Beta pilots prepared.

- Pricing sheet finalized based on validation-sprint findings (not the original illustrative FDD figures, unless confirmed unchanged).

### Success Metrics (first 30 days post-launch)

Reused from FDD Success Metrics: North Star (verified data points/month), survey completion ≥80%, brand renewal conversations initiated for all Private Beta pilots, zero P0 security/privacy incidents.

# 15. PMO Executive Dashboard & Governance Templates

## Executive Dashboard (snapshot format)

| Metric | Status |
| --- | --- |
| Overall program status | AMBER — plan complete and ready; execution has not started pending Section 18 gate |
| Current phase | Pre-Sprint-0 (Track 0 validation sprint in progress per IC Memo) |
| Budget status | Track 0: $15–25K approved and in use. Track 1 ($90–303K): not yet approved |
| Top risk | R-01 — validation sprint gate not yet confirmed passed (Section 6) |
| Next decision point | Sprint 0 Go/No-Go, contingent on Track 0 sprint outcome |

## Governance Template Set (structures, to be populated as the program runs)

| Template | Fields |
| --- | --- |
| Decision Log | Date, Decision, Owner, Rationale, Linked FDD/PRD/Architecture section, Status |
| Issue Register | ID, Description, Severity, Owner, Raised Date, Target Resolution, Status |
| Change Log | Date, Document Changed, Section, Before → After, Approved By |
| ADR (Architecture Decision Records) | ADR-000 (Technical Architecture Document itself) onward — Context, Decision, Consequences, Status |
| Assumption Log | Assumption, Source Document, Validated? (Y/N), Validation Method, Date |
| Lessons Learned | Sprint/Release, What Worked, What Didn't, Action Item, Owner |
| Status Report (weekly) | Sprint progress %, Blockers, Risks changed this week, Upcoming milestones |
| Weekly PM Report | Velocity, Burndown, Scope changes, Team capacity/availability notes |
| Steering Committee Dashboard | RAG status per epic, budget vs. actual, upcoming decisions needed from the IC |

# 16. Executive Delivery Roadmap

| Horizon | Milestone |
| --- | --- |
| 30 days | Track 0 validation sprint resolves (GO/MODIFY/NO-GO). If GO: Sprint 0 begins. |
| 60 days | Sprint 0 complete; Sprints 1–2 underway; Auth, Campaign creation, and QR redemption live in staging. |
| 90 days | MVP feature-complete (Sprints 1–4 done); Hardening (Sprint 5) begins. |
| 6 months | Private Beta running with real brand pilots; Public Beta preparation underway. |
| 12 months | Production v1.0 live; v1.1 (Rewards, Referral, automated fraud detection) in progress; Year-2 hiring (Marketing, CS, HR, Support per Blueprint) underway. |
| 24 months | v2.0 (AI Insights, Enterprise API) shipped, contingent on Egypt unit economics; GCC expansion evaluation begins only if that gate is cleared, per FDD. |

## Critical Path

Track 0 GO decision → Sprint 0 (legal + infra, especially PDPL sign-off and data-residency region) → Sprint 2 QR Redemption (highest technical risk) → Sprint 3 PDPL sign-off hard gate → Sprint 4 Analytics Report → Hardening → Private Beta real-brand validation → Production.

## Resource Allocation & Hiring Timeline

Reused directly from the Master Execution Blueprint (Phase 3): Year 1 ~10–12 people, Year 2 ~25–35, Year 3 ~50–70 (conditional). No changes made here — this document executes that plan, it does not revise it.

## Budget Timeline

| Window | Budget |
| --- | --- |
| Track 0 (now) | $15,000–25,000 (approved) |
| Sprint 0–6 (Lean MVP path) | $90,000–120,000 (per IC Memo Lean MVP alternative — recommended default over the $303K full build) |
| Monthly operating cost, post-MVP | ≈$45,000/month (per IC Memo, unvalidated until real campaigns run) |

# 17. Final Project Readiness Assessment (PMO Audit)

A genuine audit surfaces real gaps rather than rubber-stamping completeness. Findings below.

| Audit Check | Result | Note |
| --- | --- | --- |
| Missing features | None found | All 22 PRD features are backlog-mapped |
| Missing APIs | None found | All Technical Architecture Phase 8 endpoints have a backlog owner |
| Missing database entities | None found | All 12 Master PRD entities are in the WBS/backlog scope |
| Missing security requirements | None found | Section 11 maps every Technical Architecture Phase 6 control to a task |
| Missing infrastructure | None found | Section 10 covers every Technical Architecture Phase 5 component |
| Missing QA | None found | Section 9 covers every requested test type |
| Missing documentation | Partial gap | Marketing/Sales enablement content (Section 14) is flagged as owned outside Engineering/PMO — real dependency, not fully planned here |
| Missing deployment tasks | None found | Section 10 CI/CD and Section 14 Go-Live cover this |
| Missing operational tasks | None found | Section 13 covers runbooks/playbooks/escalation |
| Missing monitoring | None found | Section 10 and Section 14 cover this |
| Missing legal requirements | Real open item | AWS data-residency region and PDPL deletion-timeframe SLA are both still pending legal confirmation — flagged as R-04/R-09, not resolved by this document |
| Missing integrations | None found | Section 8 (via Technical Architecture Phase 8) covers all planned integrations |
| Orphan tasks | None found | Every backlog item traces to an Epic, which traces to a PRD feature |
| Circular dependencies | None found | Dependency Matrix (Section 5) is a DAG — no cycles |
| Sprint conflicts | None found | No story is assigned to a sprint before its dependencies' sprints |
| Impossible timeline | Not assessed against real velocity | 24-week estimate is bottom-up from story points but has not been validated against actual team throughput — first true signal arrives at Sprint 1 retro |

# 18. Critical Risks Before Development

#1 — This is not a future risk, it is the plan's current status • Per the Investment Committee Memo v1.0, only a $15,000–25,000, 60-day validation sprint is currently approved. This entire Master Delivery Plan — Sprint 0 through Production, all budget timelines, all hiring — is planned to be ready the moment that sprint clears its Go/No-Go gate, but that gate has not been confirmed passed as of this document. • Do not open Sprint 0 against this plan without an explicit GO confirmation from the Investment Committee, per IC Memo §11 criteria.

## Other critical pre-development risks

- PDPL legal sign-off (data-deletion SLA, data-residency region) is unresolved — both are hard gates for Sprint 0/3, not soft dependencies.

- QR redemption concurrency (R-03) is the single highest-severity technical risk in the MVP — recommend a Sprint 0 spike, not waiting for Sprint 2.

- Retail-partner location agreements are a Sales/Ops dependency with no engineering fallback — must be underway before Sprint 2, ideally starting in Track 0.

- Team capacity (5 engineers) against the estimated Sprint 1–4 scope has not been velocity-tested — first real signal only arrives after Sprint 1.

# 19. Recommended Development Order

Sequencing rationale, not a restatement of the sprint plan:

- 1. Legal and infrastructure foundations first (Sprint 0) — nothing else can safely proceed without PDPL sign-off kicked off and the hosting region resolved.

- 2. Identity/Auth before anything else product-facing — every other feature depends on a known user.

- 3. Fulfillment (Campaign Config → QR Redemption) before Survey — the survey has no trigger without a redemption event.

- 4. Survey before Analytics/Reporting — there is no data to report without responses.

- 5. Notifications in parallel with, not before, the fulfillment loop — they drive volume into a loop that must already work correctly.

- 6. Support and internal Admin tooling last among P0 items — necessary before real users touch the product, but not before the core loop is proven.

- 7. Hardening only after the full loop is feature-complete — security and performance work against a moving target is wasted effort.

# 20. Developer Handoff Package

Everything a new engineer or an additional engineering team needs to start without further planning.

## Document Set (read in this order)

- Founder Decisions Document v1.0 — the non-negotiables.

- Master Product Requirements Document v1.0 — what to build.

- Technical Architecture Document v1.0 — how to build it.

- This Master Delivery Plan v1.0 — when, in what order, and by whom.

## Environment Setup

- Repo access (monorepo, per Technical Architecture Phase 10).

- Local Docker Compose environment mirrors staging services.

- Staging AWS credentials via Secrets Manager (least-privilege, per role).

- Third-party sandbox credentials: SMS/OTP provider, WhatsApp BSP, payment providers.

## First-Sprint Tasks for a New Engineer

Assigned from the Section 2 backlog based on Sprint assignment and current team capacity — never from an unplanned ad hoc list. A new engineer's first task should always be the lowest-risk, best-specified item available in the current sprint (typically a P0 item already at full 20-field specification).

## Points of Contact

| Area | Contact |
| --- | --- |
| Product/scope questions | CEO (dual PM role, Year 1) |
| Architecture questions | CTO |
| Legal/compliance questions | External counsel (via CEO) |
| Ops/fulfillment questions | Ops Manager |

## Definition of "Ready to Start"

A new team is ready to begin implementation immediately once: this document set has been read, environment setup is complete, and the Track 0 GO confirmation (Section 18) has been received. Not before.