INDEPENDENT EXECUTIVE REVIEW BOARD

Enterprise Readiness Audit — Engineering Execution Gate

Tajribti (تجربتي) — Egypt's Consumer Intelligence Platform

| Field | Detail |
| --- | --- |
| Review Type | Independent readiness audit — Board is external to the product/engineering team |
| Documents Audited | IC Memo v1.0, Founder Decisions Document v1.0, Master PRD v1.0, Technical Architecture v1.0, Master Delivery Plan v1.0 (which itself contains Sprint Plan, Backlog, Release Plan, QA/Security/DevOps/AI/Ops/Go-Live Plans) |
| Authority | This Board may approve or reject. No middle ground. |
| Date | 26 July 2026 |
| Version | 1.0 — Final |

# Table of Contents

# 1. Executive Readiness Score

58 / 100 — MODERATE. Documentation is unusually thorough. Authorization to execute is not established. • The document corpus (Blueprint, FDD, PRD, Architecture, Delivery Plan) is more complete than the median pre-seed project this Board has reviewed. • The score is held down not by planning quality but by unresolved gates that planning quality cannot substitute for: no confirmed spend authorization beyond $15–25K, no legal entity confirmation, no validated demand, and several hard-blocking open decisions. • A high score on paper does not mean the team may proceed. See Section 14.

# 2. Readiness by Domain

| Domain | Score /100 | Verdict |
| --- | --- | --- |
| Business | 48 | Strategy is coherent; commercial validation is entirely absent (zero customer interviews on record) |
| Product | 70 | MVP critical-path features are genuinely well-specified; 12 of 22 features carry full 20-field/12-field specs, remainder deliberately deferred |
| Architecture | 62 | Internally consistent design; blocked by an unresolved cloud-region/data-residency decision that affects every infrastructure task |
| Engineering (Delivery/Backlog) | 64 | Backlog and WBS are usable; the Year-1 resourcing plan does not staff a Sales/Brand-Partnerships function despite a B2B-sales-led GTM strategy — see Section 9 |
| QA | 68 | Comprehensive test strategy; zero of it has been executed against real code, so its adequacy is unproven |
| Security | 52 | Strong design intent; the single hardest legal gate (PDPL sign-off) is still open and sits on the MVP critical path |
| AI | 82 | Correctly and explicitly out of MVP scope; V2 architecture is well-reasoned and not a source of current risk |
| Operations | 60 | Runbook/escalation structure exists; Marketing and Sales launch-readiness are explicitly acknowledged as outside this plan's control |
| Deployment/DevOps | 62 | Sound CI/CD and IaC approach; cannot be finalized until the region decision (see Architecture) is closed |
| Documentation | 71 | Unusually complete corpus; governance mechanisms it mandates (Decision Log, ADR log) exist only as empty templates, not populated records |

# 3. Critical Findings

CF-1 — No confirmed spend authorization beyond the validation sprint • The IC Memo v1.0 approved a $15,000–25,000, 60-day validation sprint only, with explicit Go/No-Go criteria (IC Memo §11). Every subsequent document — Blueprint, FDD, PRD, Architecture, Delivery Plan — was built as contingent planning for a GO decision that has not been confirmed as reached anywhere in this document set. • This is not a documentation gap. It is the absence of the one fact that makes everything else actionable.

CF-2 — No commercial validation evidence exists • Every plan assumes brand demand at specific price points ($4,000–20,000/campaign). Zero brand interviews, zero LOIs, and zero pricing validation appear anywhere in the document set as completed. The IC Memo's own validation-sprint design exists specifically to produce this evidence — and no output from it is referenced.

CF-3 — Legal entity and data-residency status unconfirmed • The FDD lists "Egyptian LLC initially" as a decision, not a confirmed fact of incorporation. The Technical Architecture's cloud region (UAE/Bahrain) is explicitly "pending legal confirmation of PDPL data-residency requirements" in three separate documents. Sprint 0 of the Delivery Plan assumes AWS provisioning and third-party contract signature can proceed — neither is safe to do with an unconfirmed legal entity and an undecided data-residency region.

# 4. Blocking Issues

Items that make it unsafe to authorize Sprint 0 as written, independent of the funding-gate question above.

| ID | Issue | Why It Blocks |
| --- | --- | --- |
| B-01 | PDPL legal sign-off (data deletion SLA, data residency) not obtained | TJ-008 (Consent & Privacy Center) is an FDD non-negotiable and an MVP launch gate; the Delivery Plan itself schedules this as a hard Sprint 3 gate but the underlying legal work has not started per any evidence in this document set |
| B-02 | No Sales/Brand-Partnerships role is staffed in the Sprint 0–6 Resource Plan | The GTM strategy is explicitly B2B-sales-led (FDD Sales Strategy); Sprint 6 requires 5 real brand pilots; no funded headcount exists in the Delivery Plan's own Resource Plan (Section 8) to execute this — engineering can build a product with no one selling it |
| B-03 | Cloud hosting region undecided | Every infrastructure task in DevOps/Architecture depends on this; it cannot be provisioned twice |
| B-04 | No Sprint 0 budget line for third-party contract costs | SMS/OTP, WhatsApp BSP, and payment-provider contracts are assumed signed in Sprint 0, but Track 0's approved $15–25K was scoped for validation activities (interviews, legal review, landing page) — not production vendor contracts. No budget line covers this gap in any document |

# 5. Major Issues

| ID | Issue | Domain |
| --- | --- | --- |
| M-01 | 10 of 22 PRD features have only summary-level specification (ID/priority/points), not full acceptance criteria — acceptable per the plan's own stated grooming cadence, but genuinely undefined today, not merely deferred | Product |
| M-02 | No pagination strategy is defined for any list endpoint (campaign lists, ticket lists, brand lists) across the Technical Architecture or Master PRD | API/Architecture |
| M-03 | Team-composition mismatch between the Master Execution Blueprint's Year-1 org chart (includes Head of Brand Partnerships, Data Lead) and the Delivery Plan's actual Sprint 0–6 Resource Plan (neither role appears) | Cross-document / Delivery |
| M-04 | Timeline (24 weeks to Production) is bottom-up from story points but has zero velocity data behind it — the plan itself flags this (Delivery Plan Section 17) but treats it as acceptable rather than a real scheduling risk | Delivery |
| M-05 | Working company name ("Tajribti") is used as final across every technical and product document despite the FDD explicitly listing trademark/domain clearance as an open decision — a name change after architecture/branding work begins is costly rework, not a cosmetic fix | Business/Brand |
| M-06 | No populated Decision Log, ADR log, or Change Log exists despite the FDD mandating formal amendment tracking — every correction made during this document set's own development (e.g., the Samplia founding-year correction) is traceable only in conversation history, not in a governance record | Documentation/Governance |

# 6. Minor Issues

- Illustrative pricing figures ($4,000–20,000/campaign) are repeated across FDD, PRD, and Delivery Plan without a single labeled source-of-truth version — if the validation sprint changes pricing, multiple documents need coordinated edits.

- No explicit versioning policy exists for the mobile app beyond "tied to app-store release cadence" — minimum-supported-version enforcement is mentioned once (Architecture Phase 10) but not carried into the Release Plan's Public Beta/RC criteria.

- The Escalation Matrix (Operational Readiness) names roles ("Backend/Frontend lead") that don't yet exist as confirmed hires — fine for a template, but should be flagged as provisional.

- No environmental/sustainability consideration appears anywhere despite PESTEL analysis in earlier strategic work having flagged it as a minor opportunity — not launch-relevant, but a documentation completeness gap.

# 7. Missing Decisions

Carried forward, unresolved, from the FDD's own Open Decisions section — repeated here because they remain open at time of this audit, not because they are new findings:

- Final legal company name and trademark/domain clearance.

- Whether the CEO doubles as Product Manager through Year 1 or a dedicated PM is hired on GO.

- Final cloud hosting region.

- Whether external funding is sought at all, or the company remains bootstrapped.

- Exact revenue-mix percentages, pending validation-sprint pricing findings.

New, identified by this audit:

- Who owns and funds the Sales/Brand-Partnerships function during Sprint 0–6 (Blocking Issue B-02).

- What budget line covers Sprint 0 production vendor contracts (Blocking Issue B-04).

- Whether the Egyptian LLC is actually incorporated, and by when it must be to support Sprint 0 contract signature.

# 8. Missing Documentation

- A populated Decision Log, Issue Register, and ADR log (templates exist in the Delivery Plan; no entries exist).

- A Marketing Launch Plan with the same rigor as the Sales Enablement / Go-Live checklists — currently a one-paragraph dependency flag, not a plan.

- A formal Vendor/Contract tracker for SMS, WhatsApp BSP, payment providers, and cloud hosting — referenced throughout but not consolidated anywhere.

- Legal review evidence (even a memo confirming PDPL scope) — referenced as a dependency in at least five documents, produced in none.

# 9. Cross-Document Inconsistencies

| Document A | Document B | Inconsistency |
| --- | --- | --- |
| Master Execution Blueprint (Year-1 org chart) | Master Delivery Plan (Section 8, Resource Plan) | Blueprint includes Head of Brand Partnerships and Data Lead in Year 1; Delivery Plan's actual Sprint 0–6 staffing omits both roles |
| Founder Decisions Document (Open Decisions) | Every downstream document | FDD explicitly marks the company name as unresolved; every later document uses "Tajribti" without a provisional-name caveat |
| Technical Architecture (Phase 5) | Master Delivery Plan (Sprint 0 deliverables) | Architecture says the cloud region is pending legal confirmation; Delivery Plan schedules region provisioning as a completed Sprint 0 deliverable without flagging the same open dependency at the point of execution |

No circular dependencies were found — the Delivery Plan's Dependency Matrix is a valid DAG. No duplicated decisions were found beyond the pricing-figure repetition noted in Minor Issues.

# 10. Technical Debt Risks

- Modular monolith is the correct Year-1 choice, but module boundaries have not been tested under real load — if boundaries are wrong, the "extract later" plan (Technical Architecture Phase 1) becomes expensive rework, not a clean extraction.

- QR redemption concurrency (flagged as the single highest technical risk in the Delivery Plan's own Risk Register, R-03) has a load-test plan but no load test has been run — this is a design-time assumption, not a proven property.

- Partitioning strategy for SurveyResponse/AuditLog is schema-ready but not activated — reasonable for MVP volume, but the activation trigger ("once table size crosses an operational threshold") is not owned by anyone and could be missed under real growth.

# 11. Business Risks

- Zero validated willingness-to-pay — every revenue figure in every financial projection is illustrative.

- A real, named regional competitor (Marketeers Research) already sells FMCG analytics in Egypt/KSA/GCC — the differentiation thesis (sampling-to-data pipeline) is argued, not demonstrated.

- The reference company (Samplia) itself appears to be a bootstrapped, non-venture-scale business — the plan's growth assumptions may be structurally optimistic relative to what the reference case actually proves is achievable.

- No Sales function is funded to acquire the brand pilots the entire Beta strategy depends on (see B-02).

# 12. Production Risks

- Launching with an unresolved data-residency region risks a mid-build infrastructure migration — the most expensive possible time to discover this gap.

- Launching before PDPL sign-off is a direct legal-exposure risk the FDD itself calls non-negotiable — this is not a risk to accept, it is a gate to close.

- Single-region MVP with 4-hour RTO/1-hour RPO (Technical Architecture Phase 9) is reasonable for MVP scale but has not been tested via an actual restore drill — the plan calls for quarterly drills but none has occurred yet.

# 13. Immediate Actions Required (Before Any Re-Submission to This Board)

| # | Action | Owner |
| --- | --- | --- |
| 1 | Obtain and document explicit IC confirmation that the Track 0 validation sprint cleared its Go/No-Go gate (IC Memo §11) — or, if it has not, cancel this authorization request entirely until it does | CEO / Investment Committee |
| 2 | Close the PDPL legal review and obtain written counsel sign-off on data-residency region and deletion-SLA requirements | Legal |
| 3 | Confirm Egyptian LLC incorporation status in writing before any vendor contract is signed | CEO / Legal |
| 4 | Add a funded Sales/Brand-Partnerships role to the Sprint 0–6 Resource Plan, or explicitly document who executes GTM Stage 1 outbound and from what budget | CEO / PMO |
| 5 | Add an explicit Sprint 0 budget line for production vendor contracts, separate from the Track 0 validation-sprint budget | Finance / PMO |
| 6 | Populate the Decision Log with every material decision and correction made to date, per the FDD's own amendment rule | PMO |

# 14. Final Gate Review

## Can the engineering team begin implementation tomorrow?

NO • The document corpus is implementation-ready in isolation — the PRD, Architecture, and Delivery Plan give an engineering team enough detail to start coding. • But readiness to code is not authorization to spend, and this project has neither a confirmed Go decision beyond its $15–25K validation sprint, nor closure on the legal, staffing, and budget gaps in Sections 4 and 13. • Starting Sprint 0 tomorrow would mean provisioning infrastructure in an undecided region, signing vendor contracts against an unconfirmed legal entity, and executing a Beta strategy with no funded Sales function — any one of which is independently sufficient grounds to withhold authorization.

# 15. Development Authorization Statement

This Board finds the planning documentation for Tajribti to be thorough and internally coherent to an unusual degree for a pre-development review. That is acknowledged and should not be discounted.

However, thorough planning is not the same as an authorized, de-risked, fundable program. This review identified 3 Critical Findings, 4 Blocking Issues, and 6 Major Issues that are not documentation gaps — they are open questions whose answers change what gets built, by whom, and whether the company is legally and financially positioned to build it. Chief among them: no evidence in this document set confirms that the one funding decision actually made by the Investment Committee — a $15,000–25,000 validation sprint — has concluded with a GO.

This Board does not reject the underlying strategy, the product design, or the technical architecture. It rejects proceeding to engineering execution while the funding gate, legal entity status, PDPL sign-off, and Sales resourcing remain unresolved. Close the items in Section 13 and resubmit.

❌ DEVELOPMENT NOT AUTHORIZED