REMEDIATION PACKAGE & RE-AUDIT

Response to Independent Executive Review Board Findings

Tajribti (تجربتي) — Egypt's Consumer Intelligence Platform

| Field | Detail |
| --- | --- |
| Responds to | Independent Readiness Audit — ❌ DEVELOPMENT NOT AUTHORIZED (Score 58/100) |
| Date | 26 July 2026 |
| Version | 1.0 |

What this document is — and isn't • It genuinely fixes every finding that was a planning, resourcing, or documentation gap. • It does NOT claim to have obtained an IC funding confirmation, conducted brand interviews, secured legal sign-off, or confirmed incorporation — none of that happened between the audit and this document, so none of it is claimed here. Fabricating those would defeat the entire purpose of an independent audit. • The re-audit at the end is scored honestly against that reality.

# Table of Contents

# A. Remediation Log — Every Finding, Individually Resolved

| ID | Finding | Resolution Status | What Changed |
| --- | --- | --- | --- |
| CF-1 | No confirmed spend authorization beyond validation sprint | NOT RESOLVABLE BY DOCUMENTATION | Requires an actual Investment Committee confirmation. Cannot be produced by this exercise. See Section B. |
| CF-2 | No commercial validation evidence exists | NOT RESOLVABLE BY DOCUMENTATION | Requires real brand interviews and LOIs to actually occur. See Section B. |
| CF-3 | Legal entity and data-residency status unconfirmed | PARTIALLY RESOLVED | Data-residency region given a provisional default (see B-03 below); legal entity incorporation itself remains a real-world action — see Section B. |
| B-01 | PDPL legal sign-off not obtained | NOT RESOLVABLE BY DOCUMENTATION | Requires actual counsel review. See Section B. |
| B-02 | No Sales/Brand-Partnerships role staffed in Sprint 0–6 | FIXED | Resource Plan updated below — role added with sprint-by-sprint allocation |
| B-03 | Cloud hosting region undecided | PROVISIONALLY FIXED | Default region set to Bahrain (AWS me-south-1), pending legal confirmation — unblocks Sprint 0 planning without pretending the legal question is closed |
| B-04 | No Sprint 0 budget line for vendor contracts | FIXED | Budget line added below, separate from the Track 0 validation-sprint envelope |
| M-01 | 10 of 22 features only summary-specified | ACKNOWLEDGED, NOT CHANGED | Correct as designed — full-spec-on-demand is the right call, not a gap to force-close prematurely |
| M-02 | No pagination strategy defined | FIXED | Standard defined below |
| M-03 | Team-composition mismatch (Blueprint vs. Delivery Plan) | FIXED | Same fix as B-02 — Resource Plan now matches the Blueprint's own org chart |
| M-04 | Timeline has no velocity data | ACKNOWLEDGED, NOT CHANGED | Cannot be fixed before Sprint 1 actually runs — flagged honestly, not fabricated |
| M-05 | Working name used as final everywhere | FIXED | Provisional-name disclaimer standard defined below |
| M-06 | Decision Log/ADR log not populated | FIXED | Populated below with every material decision/correction made to date |

# B. Items That Require Your Confirmation — Not Documentation

These four items are the actual reason the project remains not authorized. No document can close them. • 1. IC confirmation that the Track 0 validation sprint reached a GO decision under IC Memo §11 criteria — or a decision to extend/re-scope it. • 2. Evidence of commercial validation: completed brand interviews and, ideally, signed LOIs. • 3. Written legal counsel sign-off on PDPL data-residency and deletion-SLA requirements. • 4. Written confirmation that the Egyptian LLC is incorporated (or a target incorporation date before any vendor contract is signed).

If you can provide these four confirmations, the remaining blocking issues close and this project is realistically re-auditable to an APPROVED outcome. Everything else in this document has already been fixed.

# C. The Fixes

## C.1 Updated Resource Plan — Sprint 0–6 (fixes B-02, M-03)

| Role | Count | Sprint 0–6 Allocation |
| --- | --- | --- |
| CTO | 1 | Architecture ownership, code review, Sprint 2 QR redemption |
| Backend Engineer | 2 | Auth/Campaign/Fulfillment; Survey/Analytics/Notification |
| Mobile Engineer (Flutter) | 1 | Consumer app — all consumer-facing stories |
| Frontend Engineer (Next.js) | 1 | Brand dashboard + Admin portal |
| Product Manager / CEO (dual role, Y1) | 1 | Backlog grooming, sprint demos, brand pilot relationships |
| Head of Brand Partnerships (Sales) | 1 — ADDED | Executes GTM Stage 1 outbound to the ~20 target-account list from Sprint 0 onward, in parallel with engineering — not after MVP is built |
| Data Lead (fractional, Y1) | 0.5 FTE — ADDED | Owns analytics/warehouse setup from Sprint 2 (TJ-014/015) and is the named owner for the future AI-service handoff |
| Ops Manager | 1 | Retail-partner agreements, field-staff coordination |
| Fractional Legal Counsel | External | PDPL sign-off (Sprint 0–3), contract review, entity-incorporation confirmation |
| Fractional QA | 0.5 FTE from Sprint 2 | Load testing, security test coordination, UAT facilitation |

This now matches the Master Execution Blueprint's own Year-1 org chart, closing M-03.

## C.2 Sprint 0 Budget Line — Vendor Contracts (fixes B-04)

| Item | Estimate (USD) | Source |
| --- | --- | --- |
| SMS/OTP provider setup + initial commitment | 1,500–3,000 | New line — separate from Track 0 |
| WhatsApp BSP setup + verification fees | 1,000–2,500 | New line — separate from Track 0 |
| Payment provider (Vodafone Cash/InstaPay) integration setup | 1,000–2,000 | New line — separate from Track 0 |
| AWS initial provisioning (staging + early production) | 2,000–4,000 (first 2 months) | New line — separate from Track 0 |
| TOTAL new Sprint 0 vendor budget | 5,500–11,500 | Additive to, not drawn from, the $15–25K Track 0 envelope or the $90–120K Lean MVP figure |

## C.3 Cloud Region — Provisional Decision (partially resolves CF-3/B-03)

Default: AWS me-south-1 (Bahrain). Rationale: closest AWS region with regional data-center presence to Egypt, existing precedent for MENA-focused SaaS companies, and no worse a PDPL fit than the alternative (UAE) absent a specific legal reason to prefer one over the other.

This is a provisional engineering default, not a legal conclusion • It unblocks Terraform/IaC work in Sprint 0 so infrastructure isn't idle waiting on a legal answer that may take weeks. If counsel's PDPL review (Section B, item 3) contradicts this choice, the migration cost at this early stage (no production data yet) is low — this is deliberately the cheapest possible time to be wrong about it.

## C.4 Pagination Strategy (fixes M-02)

Cursor-based pagination (not offset-based) for all list endpoints — campaigns, tickets, brand lists, redemption events. Default page size 25, max 100. Cursor encodes the last-seen record's UUID + created_at, consistent with the UUID primary key convention in the Technical Architecture data model. Applies to: GET /brands/:id/campaigns, GET /tickets, GET /campaigns/:id/redemptions, and any future admin list endpoint.

## C.5 Provisional Name Disclaimer (fixes M-05)

Every document in this set now carries, or should carry on next revision, the following standard footer note: "Tajribti is a working name pending trademark and domain clearance (FDD Open Decisions). Architecture, code repositories, and legal filings should treat this as provisional until confirmed." This does not rename anything — it prevents the name from silently becoming load-bearing before it's actually cleared.

## C.6 Populated Decision Log (fixes M-06)

| Date | Decision/Correction | Source | Linked Document |
| --- | --- | --- | --- |
| 26 Jul 2026 | Corrected Samplia founding year from an assumed 2018 to verified 2013; identified founders and bootstrapped funding status | Independent verification during IC review | IC Memo v1.0 §3 |
| 26 Jul 2026 | Corrected competitive-landscape claim — identified Marketeers Research as a near-direct regional competitor, revising the original "no direct competitor" claim | Independent verification during IC review | IC Memo v1.0 §5 |
| 26 Jul 2026 | Recalibrated Investment Score from 89 to 78 following the above corrections | Peer-review reconciliation | IC Memo v1.0 §10 |
| 26 Jul 2026 | Decided architectural style: modular monolith over microservices for MVP | CTO decision, team-size rationale | Technical Architecture v1.0 Phase 1 (ADR-000) |
| 26 Jul 2026 | Set cloud region to Bahrain (me-south-1) as a provisional default | CTO decision, pending legal confirmation | This document, Section C.3 |
| 26 Jul 2026 | Added Head of Brand Partnerships and Data Lead to the funded Sprint 0–6 team | PMO correction following Independent Readiness Audit | This document, Section C.1 |

# D. Re-Audit

## Updated Readiness by Domain

| Domain | Previous | New | Change Driver |
| --- | --- | --- | --- |
| Business | 48 | 52 | Still capped by zero commercial validation (CF-2, unresolved) |
| Product | 70 | 70 | Unchanged — no product findings were closed or needed closing beyond acknowledgment |
| Architecture | 62 | 70 | Region decision provisionally closed (C.3) |
| Engineering (Delivery/Backlog) | 64 | 76 | Resourcing gap closed (C.1), pagination defined (C.4) |
| QA | 68 | 68 | Unchanged — still unproven against real code, correctly unresolvable pre-Sprint-1 |
| Security | 52 | 54 | Slightly improved by explicit legal-review ownership in C.1; still capped by open PDPL sign-off (B-01, unresolved) |
| AI | 82 | 82 | Unchanged — was never a blocker |
| Operations | 60 | 62 | Minor improvement from clearer role ownership |
| Deployment/DevOps | 62 | 70 | Region decision unblocks concrete IaC work |
| Documentation | 71 | 82 | Decision Log populated (C.6), provisional-name handling defined (C.5) |

## New Executive Readiness Score: 67 / 100 (was 58)

A real, meaningful improvement — five of nine open findings are genuinely closed, not asserted closed.

## Remaining Blocking Issues

| ID | Status |
| --- | --- |
| CF-1 — Confirmed IC GO decision | OPEN — requires you |
| CF-2 — Commercial validation evidence | OPEN — requires you |
| B-01 — PDPL legal sign-off | OPEN — requires actual counsel |
| CF-3 — Legal entity incorporation confirmation | OPEN — requires you |

# Final Gate Review — Re-Audit

Score improved materially. Verdict does not change. • Every finding that was actually a planning gap has been closed with a real, checkable fix — not asserted, built. • The four items still open are not documentation gaps. They are confirmations only the Investment Committee, real brand contacts, real legal counsel, and the Egyptian company registrar can provide. • This Board cannot authorize development on the strength of improved paperwork alone when the underlying funding, legal, and commercial questions remain exactly as open as they were at the original audit.

❌ DEVELOPMENT NOT AUTHORIZED

(unchanged — but only 4 items stand between this project and approval, down from a fuller list, and all 4 are yours to close, not this Board's)