INVESTMENT COMMITTEE MEMO

FINAL EDITION — VERSION 1.0

Consumer Sampling & Intelligence Platform — Egypt Market Entry

Reference Case: Samplia (Barcelona/Madrid, Spain)

| Field | Detail |
| --- | --- |
| Project | Egypt Market Entry — Consumer Sampling & Intelligence Platform |
| Reference Company | Samplia (Spain) |
| Country of Analysis | Arab Republic of Egypt |
| Document Status | FINAL — supersedes all prior drafts and working notes on this opportunity |
| Date | 26 July 2026 |
| Prepared For | Investment Committee |
| Version | 1.0 (Final) |

COMMITTEE DECISION — AT A GLANCE • Recommendation: CONDITIONAL APPROVAL — Fund a bounded discovery phase, not a full launch. • Do not fund the full build ($303k) or the lean MVP ($90–120k) yet. Fund a $15–25k, 60-day commercial validation sprint first (see Section 11). • Overall Investment Score: 78/100 (Moderate). Full scorecard in Section 10. • This is a strategy-stage opportunity, not a diligence-complete one: the core thesis is sound, the commercial evidence is not yet there.

# Table of Contents

# 1. Executive Summary

The opportunity is not a free-sample distribution app. The product is a consumer-data and brand-intelligence layer; free sampling is the low-cost mechanic that earns the right to collect permissioned, structured consumer data at scale. The paying customer is the FMCG/beauty/pharma brand manager — not the consumer who receives the sample. This reframing is the single most important strategic insight in this memo and is the basis for the entire business model recommended below.

The reference model, Samplia (Spain), is a decade-old company (founded 2013) that has reached meaningful scale — tens of millions of samples distributed, 300–400+ brands served, roughly 2 million app users — without any public record of institutional funding. That combination (durable, bootstrapped, mid-scale) points to a solid regional services business, not a proven venture-scale outcome. Egypt planning should be anchored to that base case, with platform/data-scale upside treated as stretch potential rather than the default scenario.

A literal copy of the Spanish model is not recommended. An Egypt-first redesign — portable retail-partner kiosks instead of permanent installations, an Arabic-first rewards-platform app instead of a plain sampling app, and AI-generated consumer-intelligence narratives instead of raw dashboards — has a materially stronger fit, but the commercial case remains unproven: zero customer interviews have been conducted, no bottom-up market sizing exists, and a real Egyptian/regional competitor with an FMCG analytics platform (Marketeers Research) has been identified, which narrows the differentiation claim made in earlier drafts of this analysis.

Recommendation: fund a bounded, cheap discovery phase — not the full build — with explicit go/no-go criteria before any further capital is committed.

# 2. The Opportunity

### What is being proposed

A mobile-app-linked, in-person product sampling network for the Egyptian market: consumers receive free samples of new FMCG/beauty/pharma products at retail-partner locations and pop-up sites, complete a short in-app survey immediately after trial, and brands pay for the campaign plus the resulting structured, demographically-tagged consumer data and analytics.

### The problem for brands (the real customer)

- Sample distribution today is largely unmeasured — brands don't know who received a sample, whether it was tried, liked, or led to a repeat purchase.

- Traditional market research is slow — survey design, recruitment, fieldwork, and analysis can take weeks.

- Brands need feedback within hours of product trial, not after a full research cycle.

### Core assumptions the model depends on

- Consumers will complete a short post-trial survey in exchange for a free product.

- Brands will pay a premium for attributable, tagged sampling data over traditional market research.

- The cost of distributing a sample is lower than the value of the data it generates.

- A large enough panel of verified, repeat users can be built for segment-level statistical usefulness.

Single point of failure • If Egyptian brands are not willing to pay a meaningful premium over existing market-research spend for this specific data, the model does not work regardless of execution quality. This is the one assumption that must be tested before any further capital is committed.

# 3. Reference Company — Samplia

| Attribute | Detail |
| --- | --- |
| Founded | 2013, Barcelona (current HQ reported as Madrid) |
| Founders | Arnau Lahuerta Tarré, Robert Bonada, Paula Torrell Rojas |
| Funding | Unfunded / bootstrapped per third-party company data; no public institutional rounds identified |
| Scale | ~40–50 million samples distributed; 300–400+ brands served; ~2 million app users; ~87% self-reported survey completion rate |
| Global competitive set | ~127 identified competitors, of which ~12 are funded (e.g. Localz, Grability, Snipp) |
| Core mechanic | App-linked smart vending/sampling machines in shopping centres, plus pop-up activations and retail sampling |

Investment read: a decade of survival without external funding, in a category with well over a hundred competitors globally, is consistent with a defensible-but-not-hyper-scalable niche. It supports funding an Egypt entrant as a capital-efficient regional services business; it does not, on its own, support venture-scale return assumptions.

# 4. Egypt Market Assessment

Egypt fits the underlying category — a young, mall-centric, social-media-active, urban population with rising FMCG innovation activity — but no bottom-up market sizing has yet been built for this specific product.

| Factor | Assessment | Basis |
| --- | --- | --- |
| Expected demand | Directionally high | Category analogy only — not validated by interviews |
| Brand-side readiness | Directionally high | Category analogy only |
| Consumer-side readiness | Directionally high | High urban smartphone/social penetration |
| Awareness-building need | Medium | New category for Egyptian consumers |
| Direct competition | Low–Medium | Revised upward — see Section 5 |

### Priority segments

FMCG, food, cosmetics, personal care, pharma OTC, and beverage brands, targeting consumers aged 18–40 in Cairo, Giza, and Alexandria.

# 5. Competitive Landscape

### Direct / Near-Direct

No confirmed Egyptian player replicates Samplia's exact app + smart-vending-machine sampling mechanic. However, Marketeers Research (active in Egypt, KSA, GCC, and Europe) already sells an AI-powered analytics platform ("Smart Value™") for FMCG pricing, promotion, and assortment decisions — the analytics half of the proposed value proposition already has a regional competitor. Any entrant must differentiate on the sampling-to-data pipeline specifically, not on analytics alone.

### Indirect

- Established Egypt/MENA FMCG-focused market research firms: BioNixus, Mena Intel, Spade Survey, Alkoun MEA, eMarketing Egypt.

- Traditional BTL activation agencies and mystery-shopping providers.

- Paid survey platforms and post-purchase feedback tools.

- In-store/hypermarket sampling run directly by retailers or brands.

### Global

Samplia itself competes against an estimated 127 players globally, including funded competitors. Assume that any Egyptian success will draw both local replication and international entrants into MENA.

# 6. Localization & Business Model

Position the company as a Consumer Intelligence Platform for which sampling is the acquisition mechanic — not as a sampling company.

### Required changes from the Spanish model

| Area | Egypt Approach | Priority |
| --- | --- | --- |
| Distribution | Portable kiosks via retail partners (Carrefour, Hyper One, Spinneys, Seoudi, Kazyon) and high-footfall venues, not permanent installations | Critical |
| Mobile app | Consumer Rewards Platform (points, cashback, coupons, exclusive launches) — sampling access alone will not sustain retention | Critical |
| Trust | Verified-brand badges, explicit privacy policy, no hidden subscriptions, instant rewards, QR verification | Critical |
| Language | Arabic-first, Egyptian dialect, RTL UI; English secondary | Critical |
| Payments | Consumers never pay; brands pay. Support Vodafone Cash, InstaPay, bank cards, digital vouchers for rewards | High |
| Data collection | Micro-feedback only (3–5 questions, ~30 seconds) | High |
| Analytics output | AI-generated consumer-intelligence narratives, not raw dashboards | Critical |

### Revenue streams

| Stream | Description | Illustrative Mix |
| --- | --- | --- |
| Brand campaign fee | Planning + distribution + analytics per campaign ($4,000–20,000, illustrative) | 45% |
| Per-sample distribution fee | Charged per unit for large-volume campaigns | 20% |
| AI insights dashboard | Monthly subscription for marketing/brand teams | 15% |
| Enterprise / API access | CRM integration for large accounts | 10% |
| Consumer panel / launch validation | Sell access to defined segments; premium pre-launch testing | 10% |

Not yet validated • Every price point above is illustrative and has not been tested against real Egyptian FMCG marketing budgets. This must be confirmed with 15–20 target brand contacts before pricing is finalized.

# 7. Financial Feasibility

Figures below are internally consistent scenario estimates, not validated forecasts. No unit-economics model or multi-scenario sensitivity analysis has been built — this is the largest open gap in the financial case and a precondition for full funding (see Section 11).

### Illustrative Initial Investment — Full Build

| Item | Estimate (USD) |
| --- | --- |
| Mobile app | 40,000 |
| Backend platform | 35,000 |
| AI dashboards | 20,000 |
| Website | 8,000 |
| Admin portal | 15,000 |
| Legal | 10,000 |
| Branding | 10,000 |
| Launch marketing | 40,000 |
| Office & equipment | 25,000 |
| Working capital | 100,000 |
| TOTAL | ≈ $303,000 |

### Lean MVP Alternative

≈ $90,000–120,000 with no permanent kiosks, outsourced logistics, a small team, and a Cairo-only launch.

### Illustrative Monthly Operating Cost

| Item | USD |
| --- | --- |
| Salaries | 18,000 |
| Cloud | 2,000 |
| Marketing | 8,000 |
| Logistics | 12,000 |
| Office | 2,000 |
| Legal/Admin | 3,000 |
| TOTAL | ≈ $45,000/month |

### Illustrative Three-Year Projection

| Year | Revenue | EBITDA Margin |
| --- | --- | --- |
| 1 | $500k | -20% |
| 2 | $1.8M | 12% |
| 3 | $4.2M | 24% |

Break-even: estimated 18–24 months. Gross margin: software ~70–85%, sampling ~25–45%, blended ~60%. ROI: ~3–4 years if execution succeeds — all figures illustrative and unvalidated against Egyptian cost structures.

# 8. Legal & Regulatory

- Recommended structure: Egyptian LLC initially, converting to a JSC as the company scales.

- Key statutes: Companies Law; Consumer Protection Law; Personal Data Protection Law (Law No. 151 of 2020); applicable tax and e-commerce regulations.

- Data collected (age, gender, location, product preferences, survey responses) makes privacy compliance a core operating capability. Biggest legal risk: consumer profiling, behavioral analytics, and location tracking.

- Contracts required with brands, field sampling staff, retail partners, logistics providers, and consumers (terms of use), plus a documented privacy/data-governance framework.

- Still open and required before any data-heavy MVP ships: cross-border data-transfer rules, consent-management mechanics, data-retention periods, and incident-response obligations.

# 9. Go-to-Market Strategy

This is a B2B-first business: without brand clients there is no sampling; without sampling there are no consumers; without consumers, brands will not renew. Build supply before demand.

### Sequence

- Stage 1 — Brand supply: target ~20 named companies (Coca-Cola Egypt, PepsiCo, Nestlé, Edita, Juhayna, Unilever, P&G, Henkel, EVA Pharma, Dabur, L'Oréal, Beiersdorf). Sell measurable results, not software.

- Stage 2 — Consumer acquisition: position as exclusive early access, not "free stuff." Channels: TikTok, Instagram, Facebook, university ambassadors, micro-influencers, mall activations, referrals.

- Stage 3 — Community & retention: interest-based communities (food, beauty, fitness, parents, students) double as resellable research panels and give consumers a recurring reason to open the app.

- First clients: medium-sized Egyptian brands (faster decisions, less bureaucracy) rather than global HQ-controlled accounts or early-stage startups.

## Implementation Roadmap

| Horizon | Goal | Key Milestones |
| --- | --- | --- |
| 30 days | Validate demand — write no code | 50 brand-side interviews; landing page + lead capture; LOIs from 5 companies. Fewer than 5 LOIs = do not proceed to build. |
| 90 days | Lean MVP | Admin + brand dashboards, consumer app, QR, survey, analytics (no AI/ML yet); first campaign live at 200+ users; targets: 5 brands, 1,000 samples, 80% survey completion |
| 6 months | Prove the model | 10,000 users, 15 brands, 30 campaigns; add gamification/rewards/referral; begin dashboard subscriptions |
| 12 months | Expand & add intelligence | Alexandria, Giza, New Cairo, 6th October; add AI insights, segmentation, predictive analytics; 100,000 users |
| 24 months | Regional option (conditional) | GCC expansion only if Egypt unit economics and retention are proven |

# 10. Risk Assessment

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Demand never validated with real brands | High | Critical | 30–50 structured brand interviews and LOIs before further spend |
| Competitive displacement (e.g. Marketeers Research) | Medium | High | Differentiate on the sampling-to-data pipeline; do not compete on analytics alone |
| Consumer acquisition cost higher than modeled | Medium-High | High | Pilot CAC in a single mall/university before city-wide rollout |
| Logistics cost overrun (becomes a distribution company) | Medium | High | Outsource fulfillment; no owned warehouses/fleet in year one |
| Fraudulent survey responses | High | Medium | QR + behavioral-pattern fraud detection from day one |
| Data privacy / regulatory breach | Medium | Critical | Privacy-by-design; legal review before MVP data collection begins |
| Brand builds an internal alternative | Low-Medium | High | Multi-brand diversification; contractual data-exclusivity terms |
| Insufficient funding for full build | Medium | High | Default to the lean MVP path, not the full $303k build |
| Reference model may be a services business, not venture-scale | Medium | Medium | Set targets against a profitable-services base case, not a hypergrowth case |

## Investment Scorecard

| Metric | Score | Rationale |
| --- | --- | --- |
| Investment Score | 78 / 100 | Sound thesis, unproven commercial case |
| Market Readiness | 76 / 100 | Category fit strong; demand unvalidated |
| Financial Attractiveness | 74 / 100 | No unit economics or sensitivity model yet |
| Competitive Advantage | 68 / 100 | Real regional analytics competitor identified |
| Scalability | 82 / 100 | Tempered by reference company's capital-light profile |
| Execution Difficulty | 94 / 100 (higher = harder) | Multi-disciplinary build: logistics + data + AI + B2B sales |

# 11. Committee Decision & Conditions for Approval

Decision • CONDITIONAL APPROVAL. Fund a $15,000–25,000, 60-day commercial validation sprint. Do not approve the $90–120k MVP or the $303k full build at this stage.

### Validation sprint scope (60 days, pre-funded separately from the main build budget)

- 30–50 structured interviews with Egyptian FMCG/beauty/pharma marketing, innovation, and consumer-insight decision-makers.

- Direct confirmation of whether Marketeers Research or any regional player already offers a comparable sampling-to-data product.

- At least 5 signed Letters of Intent or paid-pilot commitments from target brands.

- A bottom-up Egypt TAM model (FMCG companies × campaigns/year × average sampling/research budget × addressable share), replacing the current top-down estimate.

- Confirmed willingness-to-pay at or near the proposed $4,000–20,000 campaign price points.

### Go / No-Go criteria at the end of the sprint

- GO — full MVP funding — if 5+ LOIs are secured and at least 3 brands confirm willingness to pay within 20% of the proposed pricing.

- MODIFY — if demand is confirmed but pricing expectations are materially lower — revisit the revenue mix and cost structure before funding.

- NO-GO — if fewer than 3 brands express genuine interest after direct outreach — do not proceed to build.

## Confidence Assessment

| Dimension | Confidence | Basis |
| --- | --- | --- |
| Strategic reframing (data > product) | High | Well-supported by industry pattern and internal logic |
| Reference company facts | Moderate-High | Cross-verified across multiple independent sources |
| Egypt competitive landscape | Moderate | Named competitors verified; exact mechanic overlap unconfirmed |
| Egypt demand for the product | Low | Zero primary customer interviews to date |
| Financial projections | Low | Single scenario, no unit economics, unbenchmarked |

## Remaining Unknowns

- Whether any Egyptian/regional competitor already runs a near-identical sample-for-data mechanic.

- Actual FMCG marketing, sampling, and market-research spend in Egypt in absolute terms.

- Willingness-to-pay at the specific proposed price points.

- Samplia's actual unit economics, campaign pricing, and client retention.

- Whether Samplia or its global competitors have any existing MENA presence or expansion plans.

- Egyptian data-protection enforcement practice under Law No. 151 of 2020 as applied to consumer-profiling business models.

- Real consumer acquisition cost and retention behavior for a rewards-gated sampling app in Egypt specifically.

# Appendix — Document Provenance

This Final Edition consolidates and supersedes: an initial due-diligence draft on the Samplia/Egypt opportunity; an independently prepared screening note on an unrelated concept (subsequently found not to apply to this opportunity and excluded from the analysis); and a peer-review reconciliation that verified company facts, corrected the competitive landscape, and recalibrated the investment scorecard. All factual corrections and their sources are retained in the working file and available on request.

### Key sources

- Tracxn — Samplia company profile (founding year, founders, funding status, competitor count).

- Crunchbase — Samplia company profile.

- Samplia official site (samplia.com/en).

- Hostelco / Alimentaria trade-event materials — Samplia scale claims.

- Marketeers Research — Egypt/KSA/GCC FMCG analytics platform.

- BioNixus, Mena Intel, Spade Survey — Egypt market-research competitive landscape.